CONTROL CHECK AI

Product Requirements Document v1.1

Version 1.1 | Public Beta Cloud Deployment & Usage Validation | 26 August 2026

AI-Powered Project Control Assurance Platform

| Document | Value |
| --- | --- |
| Product | ControlCheck AI |
| Version | 1.1 |
| Status | Development Blueprint |
| Primary Market | EPC / Construction / Oil & Gas Contractors |
| Primary Users | Project Control, Project Managers, Management |
| Frontend | React + TypeScript + Tailwind + shadcn/ui |
| Backend | FastAPI + Python |
| Database | PostgreSQL |
| AI | LLM + deterministic tool/data layer |
| Analytics | Python / Pandas / NumPy / Scikit-learn |
| First Release Goal | Upload project data and produce evidence-backed findings |

Confidential working document. This PRD is intended to guide product, UX, engineering, data, and AI implementation for the first sellable version of ControlCheck AI.

# Table of Contents

1. Executive Summary

2. Product Vision & Strategy

3. Problem Statement

4. Target Market & Personas

5. Goals, Non-Goals & Success Metrics

6. Product Scope & Feature Matrix

7. User Journeys

8. Information Architecture & UX

9. Data Model & Canonical Data Contract

10. Data Ingestion & Quality Engine

11. Control Rule Engine

12. Findings & Evidence Engine

13. Project Health Scoring

14. AI Intelligence Architecture

15. AI Assistant Requirements

16. API Specification

17. Security, Multi-Tenancy & Governance

18. Reporting

19. Technical Architecture

20. MVP Roadmap & Delivery Plan

21. QA, Evaluation & Acceptance Criteria

22. Pilot & Go-to-Market

23. Pricing Hypothesis

24. Risks & Mitigations

25. Definition of Done

Appendix A: Example Rules

Appendix B: Example API Payloads

Appendix C: Demo Scenario

# 1. Executive Summary

ControlCheck AI is a SaaS platform that acts as an AI-powered project control assurance layer. It ingests project data from Excel/CSV in the MVP, normalizes it into a canonical model, runs deterministic project-control checks, identifies anomalies, links every finding to source evidence, calculates project health, and uses an LLM to explain causes, impacts, and recommended actions.

The product is intentionally not positioned as an ERP replacement, scheduling system, or generic BI dashboard. Its primary value is early detection: identify what a Project Control professional should investigate before a project issue becomes expensive or difficult to reverse.

The MVP must deliver one clear outcome: a user can create a project, upload Budget / Actual Cost / Schedule / Progress datasets, validate the data, run Control Check, and receive a prioritized list of evidence-backed findings within minutes.

## 1.1 Product Promise

“Give ControlCheck your project data and it will tell you what needs attention, why it matters, and where the evidence is.”

## 1.2 Core Differentiation

Evidence-first AI: every important statement traces to a calculation and source rows.

Domain-first rules: project-control logic is deterministic and transparent before LLM reasoning is applied.

Fast onboarding: Excel-first ingestion minimizes integration barriers.

Action orientation: findings can become accountable actions rather than ending as dashboard alerts.

Expandable platform: the same foundation can later ingest SAP, Oracle, Primavera, MS Project, APIs, and other sources.

# 2. Product Vision & Strategy

## 2.1 Vision

Become the assurance and early-warning layer for project control teams, helping them detect cost, schedule, progress, and data-quality issues before they become project problems.

## 2.2 Mission

Reduce the time required to inspect project data while improving the consistency, traceability, and actionability of project-control reviews.

## 2.3 Product Principles

Trust over novelty: deterministic calculations and evidence are more important than impressive AI language.

Smallest sellable product first: solve a narrow, recurring pain before adding enterprise breadth.

Explain every number: users should be able to inspect how metrics and findings were derived.

Human-in-the-loop: AI recommends; authorized project staff decide and act.

Progressive intelligence: data quality → rules → anomaly detection → AI reasoning → predictive capabilities.

# 3. Problem Statement

## 3.1 Current State

Project Control teams frequently work across multiple Excel files and manual monthly reviews.

Data formats differ between projects, vendors, and reporting cycles.

Review effort is high and depends heavily on individual analyst experience.

Problems can be visible in hindsight but not prioritized early enough for management.

BI dashboards show status but often do not explain what should be investigated next.

Generic LLMs can summarize files but may hallucinate, miscalculate, or lack traceability.

## 3.2 Core Pain Points

| Pain | Impact | ControlCheck Response |
| --- | --- | --- |
| Manual cross-checking | Hours spent comparing datasets | Automated deterministic checks |
| Inconsistent Excel schemas | Slow preparation and cleaning | AI-assisted schema mapping + canonical model |
| Hidden cost leakage | Potential financial exposure | Variance, commitment, transaction, and anomaly rules |
| Schedule slippage discovered late | Reduced recovery options | Progress / baseline / actual checks |
| Weak evidence traceability | Low trust in AI outputs | Evidence Engine linking findings to records |
| Too many alerts | Alert fatigue | Severity + confidence + prioritization |
| Reporting overhead | Time spent writing monthly reports | AI-assisted executive summary and PDF report |

# 4. Target Market & Personas

## 4.1 Ideal Customer Profile

| Dimension | Initial ICP |
| --- | --- |
| Industry | EPC, construction, oil & gas services, selected mining contractors |
| Company size | 50–500 employees |
| Active projects | 5–30 projects |
| Project value | Typically Rp10B–Rp1T+ |
| Current workflow | Excel-heavy monthly project controls |
| Buyer | Project Controls Manager / PMO / Operations Director |
| Economic value | Reduce review time and expose material risks earlier |

## 4.2 Personas

| Persona | Jobs-to-be-done | Pain | Key Product Need |
| --- | --- | --- | --- |
| Project Control Engineer | Prepare and review project data | Manual reconciliation | Fast findings with evidence |
| Project Control Manager | Challenge project performance | Limited time across projects | Portfolio view + prioritization |
| Project Manager | Understand what needs intervention | Too many reports, too little insight | Root cause + action recommendations |
| Management / Director | See material exposure and trend | Information is fragmented | Executive health + top risks |
| Admin / Data Steward | Maintain projects and datasets | Formatting inconsistency | Validation, access, audit trail |

# 5. Goals, Non-Goals & Success Metrics

## 5.1 MVP Goals

Support organization and project creation.

Accept XLSX/CSV project datasets.

Map source columns to canonical fields.

Perform data-quality checks before analysis.

Run a rule library across cost, schedule, progress, and data quality.

Generate findings with severity, impact, confidence, and evidence.

Calculate a transparent project health score.

Provide evidence-backed AI explanations and Q&A.

Generate an executive report.

Provide an auditable history of analysis runs.

## 5.2 Non-Goals for MVP

No ERP replacement.

No full scheduling authoring or Primavera editing.

No automated financial posting.

No autonomous contract changes or approvals.

No multi-agent swarm architecture.

No mobile app requirement.

No enterprise SSO requirement unless a pilot needs it.

No predictive EAC model as a release blocker; it is a later enhancement.

## 5.3 North-Star Metrics

| Metric | Definition | MVP Target |
| --- | --- | --- |
| Finding Precision | Validated useful findings / reviewed findings | ≥70% initial; >85% after pilot iteration |
| Time-to-Insight | Upload complete → first findings visible | <5 minutes for standard dataset |
| Data Mapping Success | Columns mapped without manual custom coding | ≥80% for supported templates |
| Evidence Coverage | Material findings with source evidence | 100% |
| False Positive Rate | Findings rejected by domain reviewer | <30% initial |
| User Time Saved | Manual review time vs ControlCheck review time | ≥50% target |
| Pilot Activation | Pilot projects completing first analysis | ≥80% |

# 6. Product Scope & Feature Matrix

| Module | MVP | Post-MVP | Notes |
| --- | --- | --- | --- |
| Authentication & Organization | Deferred in Phase 4A | SSO / SCIM | Tenant isolation now; authentication and complete RBAC later |
| Projects | Yes | Portfolio planning | Core tenant boundary |
| Data Upload | Yes | ERP/API connectors | XLSX/CSV first |
| Schema Mapping | Yes | Template learning | AI-assisted suggestions |
| Data Quality | Yes | Continuous monitoring | Pre-check gate |
| Cost Control | Yes | Predictive EAC | Rules first |
| Schedule Control | Yes | Primavera integration | Baseline vs actual |
| Progress Control | Yes | Forecasting | Plan vs actual |
| Findings | Yes | Workflow automation | Central intelligence object |
| Evidence | Yes | Advanced lineage | Critical differentiator |
| Health Score | Yes | Custom weighting | Transparent formula |
| AI Assistant | Yes | Agentic workflows | Evidence-grounded |
| Reports | Yes | Template builder | PDF first |
| Actions | Yes (basic) | Workflow / reminders | Accountability layer |
| Billing | Basic / manual | Stripe or local billing | After pilot |
| Integrations | No | SAP/Oracle/P6/MSP/API | Roadmap |

# 7. User Journeys

## 7.1 First-Time Project Setup

User signs in.

Creates or selects organization.

Creates project with name, code, project type, currency, start/end date.

Uploads first dataset.

System detects sheets and candidate schemas.

User reviews suggested mappings.

System validates data and shows quality summary.

User fixes errors or accepts warnings.

System stores normalized data and creates an analysis run.

## 7.2 Run Control Check

User clicks Run Control Check.

System snapshots the normalized dataset version.

Rule Engine executes supported checks.

Analytics Engine computes derived metrics.

Anomaly detection runs where sufficient data exists.

Finding Engine deduplicates and prioritizes findings.

Evidence Engine attaches source records and calculations.

Health Engine calculates scores.

AI Reasoning generates explanations and recommendations for supported high-value findings.

Dashboard updates with results and run timestamp.

## 7.3 Investigate Finding

Open Findings.

Filter by severity/category/WBS/date.

Open finding detail.

Review metric and impact.

Inspect evidence rows.

Read AI explanation.

Create or assign action.

Mark finding as accepted, rejected, resolved, or needs review.

# 8. Information Architecture & UX

## 8.1 Primary Navigation

Dashboard
Projects
Data
Findings
Cost
Schedule
Progress
AI Assistant
Reports
Settings

## 8.2 Main Screens

| Screen | Purpose | Key Components |
| --- | --- | --- |
| Dashboard | Executive project view | Health score, KPI cards, top findings, trend, actions |
| Projects | Project portfolio | Project cards/table, status, health, last check |
| Project Overview | Project context | Health, datasets, latest run, top findings |
| Data Upload | Ingest data | Upload, sheet detection, mapping, validation |
| Data Quality | Improve trust | Quality score, errors/warnings, row evidence |
| Findings List | Prioritize issues | Severity filters, category, WBS, impact |
| Finding Detail | Investigate | Why, impact, evidence, AI, action |
| Cost | Cost analysis | Budget/actual/variance, drivers, trends |
| Schedule | Schedule analysis | Progress, delays, baseline vs actual |
| Progress | Progress control | Planned vs actual, WBS heatmap |
| AI Assistant | Ask questions | Conversation + evidence references |
| Reports | Generate/share | Monthly report, PDF export |
| Settings | Tenant/project controls | Users, roles, thresholds, preferences |

## 8.3 UX Principles

Critical information above the fold.

Use red/amber/green only for semantic status, not decoration.

Every major metric must have a tooltip or formula reference.

Never hide source evidence behind AI-only prose.

Keep finding investigation within 1–2 clicks from dashboard.

Long-running analysis must expose progress and run status.

# 9. Data Model & Canonical Data Contract

## 9.1 Core Entities

organizations
  └── users
  └── projects
       ├── datasets
       ├── budget_lines
       ├── actual_cost_lines
       ├── schedule_activities
       ├── progress_snapshots
       ├── analysis_runs
       ├── findings
       ├── evidence_links
       └── actions

## 9.2 Entity Definitions

| Entity | Purpose | Important Fields |
| --- | --- | --- |
| organizations | Tenant boundary | id, name, status, plan |
| users | Identity | id, organization_id, role, email, status |
| projects | Project master | id, organization_id, code, name, currency, dates, status |
| datasets | Imported source | id, project_id, type, file_name, version, checksum, status |
| budget_lines | Canonical budget | id, project_id, wbs_code, cost_code, amount, period |
| actual_cost_lines | Canonical cost transactions | id, project_id, date, wbs_code, cost_code, vendor, po_number, amount, source_row |
| schedule_activities | Canonical schedule | id, project_id, activity_id, wbs_code, baseline dates, actual dates, progress, status |
| progress_snapshots | Period progress | id, project_id, period, wbs_code, planned_pct, actual_pct |
| analysis_runs | Immutable analysis execution | id, project_id, dataset_version, started_at, completed_at, status, engine_version |
| findings | Primary intelligence object | id, run_id, category, severity, title, impact, confidence, status |
| evidence_links | Finding traceability | id, finding_id, dataset_id, source_row, record_id, calculation_ref |
| actions | Remediation workflow | id, finding_id, owner_id, due_date, status, notes |

## 9.3 Canonical Dataset V1

| Dataset | Required | Fields |
| --- | --- | --- |
| Budget | Yes | project_id, wbs_code, cost_code, description, budget_amount |
| Actual Cost | Yes | transaction_date, project_id, wbs_code, cost_code, vendor, po_number, description, actual_amount |
| Schedule | Yes | activity_id, wbs_code, activity_name, baseline_start, baseline_finish, actual_start, actual_finish, planned_progress, actual_progress, status |
| Progress | Recommended | period, wbs_code, planned_progress, actual_progress |

## 9.4 Data Type Rules

Dates stored as ISO date/time in UTC or project timezone metadata.

Money stored as numeric decimal; no floating-point persistence for financial values.

Percentages stored as decimal 0–1 internally and formatted as 0–100% in UI.

Source row and source file metadata retained for traceability.

All imported records receive a stable surrogate ID and source checksum.

# 10. Data Ingestion & Quality Engine

## 10.1 Ingestion Pipeline

Upload → File Scan → Sheet Detection → Schema Detection → Mapping Suggestions → Validation → Normalization → Quality Score → Ready for Analysis

## 10.2 Data Quality Rules

| Rule | Example | Severity |
| --- | --- | --- |
| Missing required field | WBS missing | Critical if > threshold |
| Invalid date | Finish < Start | Critical |
| Invalid percentage | Progress >100% | Warning/Critical |
| Negative cost | Actual cost <0 | Warning |
| Duplicate transaction | Same vendor/date/PO/amount | Warning |
| Orphan WBS | Actual WBS absent from budget | Critical/Warning |
| Unmapped column | Source column not mapped | Warning |
| Inconsistent vendor | “ABC Ltd” vs “PT ABC” | Warning |
| Currency inconsistency | USD rows in IDR project | Critical |
| Schema drift | Columns changed vs prior version | Warning |

## 10.3 Analysis Gate

A project can run analysis with warnings, but critical data-quality errors that make a metric unreliable must block the affected rule family. The UI must state exactly what is blocked and why.

# 11. Control Rule Engine

## 11.1 Rule Architecture

Rule Definition → Scope → Input Query → Calculation → Threshold → Severity → Finding Template → Evidence Query

## 11.2 Rule Object

{
  "rule_code": "COST-OVR-001",
  "category": "COST",
  "name": "Actual exceeds budget",
  "version": "1.0",
  "thresholds": {"warning": 0.05, "critical": 0.10},
  "requires": ["budget", "actual_cost"],
  "evidence_fields": ["wbs_code", "source_row"]
}

## 11.3 Initial Rule Families

| Family | Initial Rules |
| --- | --- |
| Cost | Actual > budget; actual variance; commitment > budget; cost spike; unallocated cost; duplicate payment-like records |
| Schedule | Overdue activity; baseline/actual slip; planned vs actual progress; critical activity delay |
| Progress | Actual below plan; progress stagnation; progress >100%; cost rising while progress flat |
| Data Quality | Missing fields; duplicates; invalid values; orphan WBS; schema drift |
| Cross-Domain | Cost rising + progress flat; schedule slip + high remaining cost; WBS performance concentration |

## 11.4 Threshold Configuration

Default thresholds ship with the product, but Project Control Managers can configure supported thresholds at organization or project level. Changes are versioned and included in analysis-run metadata.

## 11.5 Rule and Threshold Governance

Every analysis run is bound to an immutable rule-catalogue version. Each structured runtime definition declares its evaluation grain, operator, thresholds, severity bands, lookback, materiality, and permitted exclusions. Dataset, catalogue, and ground-truth versions must be recorded with the run for reproducibility.

CST-004 uses the WBS|VENDOR grain so vendor concentration is never ambiguous across work packages.

CST-005 triggers only when a transaction is at least 25% of WBS budget and at least 3% of project budget.

PRG-003 applies a current-period materiality floor of 1% of project budget before cost-growth logic is evaluated.

Threshold or severity changes require a new catalogue version, boundary tests, adjudication rationale, and regression evidence.

## 11.6 Approved Exceptions

An Approved Exception is an explicit governance record, not silent suppression. It requires an exception ID, rule/entity scope, rationale, approver, effective period, and evidence reference. Expired or unmatched exceptions do not alter findings.

Raw results always retain the finding and the applicable exception reference.

Exception-aware quality metrics may exclude approved cases from FP/FN counts while raw metrics remain visible.

Front-loaded procurement or advance-payment patterns may be approved only through this controlled mechanism.

# 12. Findings & Evidence Engine

## 12.1 Severity

| Severity | Meaning | Default Criteria |
| --- | --- | --- |
| Critical | Immediate management attention | High impact, material exposure, or severe control failure |
| Warning | Needs investigation | Meaningful deviation or emerging risk |
| Observation | Useful insight | Non-critical anomaly or improvement opportunity |

## 12.2 Finding Lifecycle

NEW → REVIEWING → ACCEPTED / REJECTED / ACTION_CREATED → IN_PROGRESS → RESOLVED

## 12.3 Evidence Requirement

No material finding should be presented as a confirmed issue without a machine-readable evidence path. For derived findings, the system stores the formula/reference plus the source records used in the calculation. AI-generated narrative may paraphrase, but cannot create unsupported values.

## 12.4 Finding Priority

A default priority score can combine severity, impact, confidence, recurrence, and age. The formula must remain inspectable and configurable rather than being hidden inside the LLM.

Priority = 0.35 × SeverityScore + 0.30 × ImpactScore + 0.20 × ConfidenceScore + 0.10 × RecurrenceScore + 0.05 × AgeScore

# 13. Project Health Scoring

## 13.1 Initial Model

Health Score = 0.30 × Cost Score + 0.30 × Schedule Score + 0.25 × Progress Score + 0.15 × Data Quality Score

## 13.2 Score Bands

| Score | Band | Interpretation |
| --- | --- | --- |
| 80–100 | Healthy | No material control concern |
| 65–79 | Moderate Risk | Management attention recommended |
| 50–64 | High Risk | Active intervention likely required |
| 0–49 | Critical | Immediate review required |

## 13.3 Transparency Requirement

Every score must provide component scores, weights, key drivers, and a “Why this score?” view. Future customer-specific scoring can override weights only through a controlled configuration.

# 14. AI Intelligence Architecture

## 14.1 AI Principle

The LLM is a reasoning and communication layer, not the source of truth for calculations. SQL/Python/rules determine facts; the LLM interprets those facts within a constrained context.

## 14.2 Architecture

React AI Assistant
      ↓
FastAPI AI Gateway
      ↓
Intent + Permission Check
      ↓
Tool Planner
      ↓
Controlled Data Tools
      ├─ get_project_health
      ├─ get_cost_variance
      ├─ get_top_cost_drivers
      ├─ get_delayed_activities
      ├─ get_finding_evidence
      └─ get_progress_trend
      ↓
Context Builder
      ↓
LLM Reasoning
      ↓
Structured Answer + Evidence References

## 14.3 AI Safety Rules

Never invent financial values, activity IDs, dates, or evidence.

State when required data is unavailable.

Use “potential exposure” rather than “loss” unless the evidence establishes an actual loss.

Do not issue accounting, contractual, or legal decisions autonomously.

Respect tenant/project access before any tool call.

Log prompt template version, tool calls, source IDs, and model response metadata for auditability where policy permits.

# 15. AI Assistant Requirements

## 15.1 Supported Query Types

| Intent | Example | Required Tools |
| --- | --- | --- |
| Health explanation | Why is health score 68? | get_project_health, top_findings |
| Cost drivers | What caused the cost variance? | get_cost_variance, get_top_cost_drivers |
| Schedule risk | Which activities are most at risk? | get_delayed_activities |
| Finding investigation | Show evidence for WBS 03.02 overrun. | get_finding_evidence |
| Action planning | What should I do first this week? | get_top_findings, action context |
| Comparison | Which WBS is worst? | get_wbs_performance |

## 15.2 Response Structure

Answer
Key Evidence
Impact
Recommended Action
Confidence / Data Caveat
Evidence References

## 15.3 AI Evaluation

A golden-question test set should be maintained from pilot data. Each answer is evaluated for factual correctness, evidence alignment, completeness, and usefulness by a domain reviewer.

# 16. API Specification

## 16.1 Authentication (Deferred)

| Method | Endpoint | Purpose |
| --- | --- | --- |
| POST | /api/v1/auth/login | Login |
| POST | /api/v1/auth/refresh | Refresh session |
| GET | /api/v1/me | Current user |

## 16.2 Projects & Datasets

| Method | Endpoint | Purpose |
| --- | --- | --- |
| GET | /api/v1/projects | List projects |
| POST | /api/v1/projects | Create project |
| GET | /api/v1/projects/{id} | Project detail |
| POST | /api/v1/projects/{id}/datasets/upload | Upload dataset |
| GET | /api/v1/datasets/{id}/mapping | Get mapping suggestions |
| POST | /api/v1/datasets/{id}/mapping/confirm | Confirm mapping |
| GET | /api/v1/datasets/{id}/quality | Quality result |

## 16.3 Analysis & Findings

| Method | Endpoint | Purpose |
| --- | --- | --- |
| POST | /api/v1/projects/{id}/analysis-runs | Start analysis |
| GET | /api/v1/analysis-runs/{id} | Run status |
| GET | /api/v1/projects/{id}/findings | List findings |
| GET | /api/v1/findings/{id} | Finding detail |
| GET | /api/v1/findings/{id}/evidence | Evidence records |
| POST | /api/v1/findings/{id}/actions | Create action |
| PATCH | /api/v1/actions/{id} | Update action |

## 16.4 AI & Reports

| Method | Endpoint | Purpose |
| --- | --- | --- |
| POST | /api/v1/ai/chat | Evidence-grounded assistant |
| POST | /api/v1/reports/project/{id}/monthly | Generate monthly report |
| GET | /api/v1/reports/{id} | Report status/download metadata |

## 16.5 API Standards

JSON response envelope with request_id.

Validation errors use structured codes.

Pagination for lists.

Idempotency keys for uploads and analysis runs.

OpenAPI generated from FastAPI.

Every mutating request records actor and timestamp.

# 17. Security, Multi-Tenancy & Governance

## 17.1 RBAC (Deferred)

| Role | Core Permissions |
| --- | --- |
| Org Admin | Manage users, projects, settings, plan |
| Project Control Manager | Create/edit projects, run analysis, review findings, manage actions |
| Project Control Engineer | Upload data, run analysis, investigate findings |
| Project Manager | View project findings, create/track actions |
| Viewer | Read-only dashboards/reports |

## 17.2 Tenant Isolation

Every business row carries organization_id directly or through controlled project relation.

Backend authorization checks are mandatory; frontend hiding is not security.

Object-storage paths are tenant-scoped.

Export endpoints enforce the same access model.

Audit events retain actor, object, action, and timestamp.

## 17.3 Data Governance

Uploaded source files are immutable by default after successful import; corrections create a new version.

Analysis runs are immutable snapshots.

Deletion should support soft-delete plus governed retention.

Sensitive project data should not be used for model training by default unless the customer explicitly opts in under applicable agreements.

# 18. Reporting

## 18.1 Monthly Control Report

| Section | Content |
| --- | --- |
| Executive Summary | Health, major movements, critical findings |
| Cost | Budget, actual, variance, top drivers |
| Schedule | Planned vs actual, delayed activities |
| Progress | Plan vs actual, WBS exceptions |
| Data Quality | Quality score, blocking issues |
| Findings | Top prioritized findings with impact |
| Actions | Open actions, owners, due dates |
| AI Commentary | Concise evidence-backed narrative |

## 18.2 Report Rules

Report values must come from the same analysis-run snapshot shown in the application.

AI narrative must reference the run context and not current unsnapshotted data.

PDF must include report date, project code, analysis version, and data period.

# 19. Technical Architecture

## 19.1 Application Stack

| Layer | Technology | Reason |
| --- | --- | --- |
| Frontend | React + TypeScript | Production SaaS UX |
| UI | Tailwind + shadcn/ui | Consistent enterprise components |
| Data fetching | TanStack Query | Server-state management |
| Charts | Recharts / suitable chart library | Fast implementation |
| Backend | FastAPI + Python | Strong fit for analytics and API |
| ORM | SQLAlchemy + Alembic | PostgreSQL migrations |
| Database | PostgreSQL | Multi-tenant transactional foundation |
| Analytics | Pandas / NumPy / Scikit-learn | Project-control calculations and anomaly detection |
| File storage | S3-compatible / Supabase Storage | Source files and generated artifacts |
| Background jobs | Celery/RQ or managed queue later | Long-running analysis |
| Observability | Structured logs + error monitoring | Pilot reliability |

## 19.2 Service Boundaries for MVP

Keep the codebase modular but deploy as a small number of services. Recommended MVP: one React frontend, one FastAPI application, one worker process for analysis jobs, PostgreSQL, and object storage. Split into independent microservices only when scale or team ownership requires it.

## 19.3 Processing Model

Web Request
   ↓
Create Analysis Run
   ↓
Queue Job
   ↓
Worker
  ├─ Load normalized data
  ├─ Data quality gate
  ├─ Rule execution
  ├─ Metrics / anomalies
  ├─ Findings + evidence
  ├─ Health score
  └─ AI enrichment
   ↓
Persist results
   ↓
Frontend polling / websocket update

# 20. MVP Roadmap & Delivery Plan

## Sprint 1 — Product & Data Foundation

Finalize PRD and acceptance criteria.

Create PostgreSQL schema/migrations.

Define canonical datasets and sample templates.

Prepare dummy EPC project dataset.

Define initial rule catalog.

## Sprint 2 — Ingestion & Data Quality

Project CRUD.

XLSX/CSV upload.

Sheet/column detection.

Mapping UI and mapping persistence.

Normalization pipeline.

Data quality engine and UI.

## Sprint 3 — Control & Findings

Complete adjudication, Golden Positive, and Boundary / Negative validation alignment before frontend or AI reasoning expansion.

Cost rule engine.

Schedule rule engine.

Progress rule engine.

Cross-domain checks.

Finding object and lifecycle.

Evidence engine.

## Sprint 4 — Health & AI

Health score.

Top drivers.

AI explanation.

AI Assistant with controlled tools.

Golden-question evaluation set.

## Sprint 5 — Production UX & Reporting

React dashboard.

Finding detail.

Actions.

Monthly report.

Audit log basics.

Performance hardening.

## Sprint 6 — Pilot

Deploy production pilot.

Onboard 2–3 project teams.

Measure precision and time saved.

Fix false positives.

Prepare pricing and sales demo.

# 21. QA, Evaluation & Acceptance Criteria

## 21.1 Test Layers

Unit tests for every rule calculation.

Integration tests for ingestion → normalization → finding.

API contract tests.

UI smoke tests for core journey.

Golden dataset regression tests.

AI evaluation tests for factuality and evidence alignment.

## 21.2 Key Acceptance Criteria

| ID | Acceptance Criterion | Pass Condition |
| --- | --- | --- |
| AC-01 | Upload Excel | Supported XLSX uploads without data loss |
| AC-02 | Schema mapping | User can review and confirm mappings |
| AC-03 | Quality gate | Critical issues clearly block affected analyses |
| AC-04 | Rule correctness | Known test cases produce expected values |
| AC-05 | Evidence | Every material finding has evidence reference |
| AC-06 | Health score | Score reproduces from documented formula |
| AC-07 | AI grounding | AI answer cites available evidence and avoids invented numbers |
| AC-08 | Tenant isolation | Cross-organization project access is rejected server-side; full RBAC is deferred |
| AC-09 | Report consistency | PDF values match selected analysis run |
| AC-10 | Performance | Standard pilot dataset returns initial result within agreed target |

## 21.3 Ground-Truth Governance

Ground truth must be curated independently from production rule functions. It is exhaustive for each controlled fixture and stores a unique rule/entity match key, expected severity, metric expectations, evidence anchors, and an adjudication reference. Any label change requires rationale and version history.

Golden Positive v0.2 contains 59 exhaustive expected findings across all 20 deterministic rules.

Boundary / Negative v0.2 contains 50 literal below, equal, above, and approved-exception cases across 16 numeric rules.

Representative or selectively planted labels must not be described as exhaustive ground truth.

## 21.4 Validation Metrics

Release acceptance requires 100% on controlled validation fixtures for precision, recall, severity accuracy, and metric agreement; zero unreviewed labels; zero unexplained FP/FN; and deterministic repeated output. This is not a customer-accuracy claim and must not be presented as performance on unseen project data.

Golden Positive v0.2 verified result: 59 TP, 0 FP, 0 FN, and 100% severity and metric agreement.

Boundary / Negative v0.2 verified result: 0 FP, 0 FN, with all 50 manifest cases reconciled.

Raw and exception-aware metrics are reported together; approved exceptions remain auditable.

## 21.5 Artifact Version Compatibility

Before any rule executes, dataset, rule catalogue, and ground truth must share the same major/minor version. A mismatch stops processing, writes no findings output, and returns the stable error code incompatible_artifact_versions through CLI and API.

# 22. Pilot & Go-to-Market

## 22.1 Pilot Offer

Offer a tightly scoped 30-day pilot to a small number of contractors. The pilot should use one real project per customer and focus on a measurable before/after outcome.

## 22.2 Pilot Questions

How long does the team spend preparing data today?

Which checks are repetitive?

Which findings are considered useful?

Which findings are false positives?

Which findings changed a project decision?

How much time was saved?

What value did the customer estimate from early detection?

## 22.3 Sales Demo Story

Upload messy project Excel.

Show automated mapping and data-quality issues.

Run Control Check.

Show health score and top 5 findings.

Open one cost finding.

Show source rows/evidence.

Ask AI why the issue happened.

Create an action for the responsible owner.

Generate monthly executive report.

# 23. Pricing Hypothesis

| Tier | Indicative Price | Scope |
| --- | --- | --- |
| Starter | Rp999K/month | Up to 3 projects, basic findings, PDF |
| Professional | Rp3.5M/month | Up to 10 projects, AI Assistant, team access |
| Business | Rp8–15M/month | More projects, controls, reporting, priority support |
| Enterprise | Custom | Private deployment, SSO, integrations, custom policies |

Pricing is a hypothesis for validation, not a fixed market claim. The pilot should test willingness-to-pay against measurable time saved and potential exposure identified.

# 24. Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| False positives | Low trust | Domain review, rule tuning, confidence and evidence |
| Messy data | Failed onboarding | Strong data-quality and mapping layer |
| AI hallucination | High trust/compliance risk | Tool-based grounding and evidence constraints |
| Too broad scope | Slow MVP | Hard MVP boundaries |
| Low customer urgency | Weak sales | Sell measurable early-warning value |
| Security concerns | Enterprise blockers | Tenant isolation, audit trail, clear data policy |
| Over-reliance on one LLM | Cost/vendor risk | Provider abstraction in AI gateway |
| Performance on large files | Poor UX | Async processing and staged profiling |

# 25. Definition of Done

ControlCheck AI MVP is considered ready for pilot when all of the following are true:

A real user can create an organization and project.

A real user can upload the four supported dataset types.

Mapping can be reviewed and confirmed without developer intervention.

Data quality results are visible and actionable.

All 20 deterministic rules meet the governed v0.2 controlled-fixture acceptance gates before pilot use.

Findings are prioritized and have evidence.

Health score is reproducible and explainable.

AI Assistant can answer a defined set of questions using controlled tools.

PDF report is generated consistently from an analysis run.

Phase 4A tenant predicates prevent cross-organization access; full RBAC is deferred.

Pilot logging captures analysis failures and AI evaluation data.

The product can be deployed from a reproducible environment.

# Appendix A: Example Rules

## A1. COST-OVR-001 — Actual Exceeds Budget

Scope: WBS
Formula: Variance = Actual - Budget
Critical if Variance / Budget >= 10%
Warning if >= 5% and <10%
Evidence: budget rows + actual rows
Finding: “Potential cost overrun on {wbs_code}”

## A2. COST-SPIKE-001 — Spending Acceleration

Compare current period spending with trailing average or prior comparable period.
Trigger when increase exceeds configured threshold and minimum transaction volume is met.
Do not trigger when dataset coverage is insufficient.

## A3. SCHED-SLIP-001 — Baseline Finish Slippage

Trigger when actual_finish > baseline_finish OR current date > baseline_finish for incomplete activity.
Severity increases for critical activities and larger delay days.

## A4. PROG-GAP-001 — Planned vs Actual Progress

Gap = Planned Progress - Actual Progress
Warning at configured gap threshold; Critical when combined with cost/schedule deterioration.

## A5. CROSS-COSTPROG-001 — Cost Rising While Progress Flat

Trigger when cost trend is increasing materially while actual progress remains flat within tolerance.
Recommend review of productivity, quantities, vendor charges, and potential rework.

# Appendix B: Example API Payloads

## B1. Create Analysis Run

{
  "project_id": "proj_123",
  "dataset_ids": ["ds_budget_01", "ds_cost_01", "ds_sched_01", "ds_prog_01"],
  "rule_set_version": "v1.0",
  "options": {"enable_anomaly_detection": true, "enable_ai_enrichment": true}
}

## B2. Finding Response

{
  "id": "finding_001",
  "severity": "CRITICAL",
  "category": "COST",
  "title": "Potential cost overrun on WBS 03.02",
  "metric": {"budget": 1000000000, "actual": 1240000000, "variance": 240000000},
  "confidence": 0.91,
  "impact_type": "POTENTIAL_EXPOSURE",
  "evidence_count": 14,
  "status": "NEW"
}

# Appendix C: Demo Scenario

Demo project: “EPC Tank Farm Expansion” with a 12-month baseline. The sample package should contain 1–2 thousand actual-cost rows, 100–300 schedule activities, monthly progress, and intentionally seeded control issues. Expected seeded issues include one WBS cost overrun, two overdue activities, one orphan WBS, duplicate transactions, a progress gap, and a cost-versus-progress anomaly.

The demo goal is not to show the largest number of alerts. It is to demonstrate that ControlCheck finds a small number of meaningful issues, explains them clearly, and lets the user inspect the supporting evidence.

# Document Change Log

## Change Log v0.2

Validation Alignment v0.2 formalizes rule and threshold governance, approved exceptions, exhaustive ground-truth governance, controlled-fixture metrics, artifact compatibility, and the validation-before-UI roadmap gate.

| Version | Date | Change | Owner |
| --- | --- | --- | --- |
| 0.1 | 17 Aug 2026 | Initial product requirements baseline | Product / Founder |
| 0.2 | 17 Aug 2026 | Validation Alignment: governed rules, fixtures, ground truth, metrics, exceptions, and version preflight | Product / Founder |

# Phase 4A Product Alignment

Phase 4A turns the validated deterministic engine into a durable, organization-scoped backend. It preserves the stateless audit endpoint while adding registered projects, uploaded workbook storage, dataset snapshots, reproducible rule catalogue versions, analysis-run history, persisted findings/evidence, lifecycle status updates, and audit events.

## Scope delivered in Phase 4A

PostgreSQL 15+ persistence managed by SQLAlchemy 2 and Alembic migrations.

Local atomic file-storage adapter with path-safety controls and SHA-256 integrity metadata.

Organization-scoped project creation/listing using the temporary X-Organization-ID contract.

Durable analysis execution with Golden and Boundary workbook behavior preserved.

Run history, finding filters, detailed evidence retrieval, and governed finding status transitions.

Stable API error envelope and request ID for operational traceability.

## Explicit deferrals and sequencing

Authentication and complete RBAC are deferred to a later hardening phase. The temporary organization header is suitable only for controlled development and validation environments, not public production exposure.

Phase 4B will add raw-row lineage and canonical WBS, budget, cost, commitment, schedule, and progress facts. This preserves the Phase 4A delivery focus while preparing database-native analytics and richer exception processing.

Frontend implementation remains outside the current phase. The backend contracts should stabilize before UI workflows are built.

## Acceptance criteria added in v0.3

Golden workbook creates one succeeded run with 59 findings and source-traceable evidence.

Boundary workbook creates one succeeded run with zero findings.

Workbook/project identity mismatch creates no analysis run.

Engine failure creates one failed run and no findings.

Cross-organization access returns not found and never leaks tenant records.

Alembic upgrade, downgrade, re-upgrade, and zero-drift checks pass against PostgreSQL.

All versioned historical reference artifacts remain byte-for-byte unchanged.

## Change Log

| Version | Date | Change |
| --- | --- | --- |
| 0.1 | 17 Aug 2026 | Initial MVP blueprint. |
| 0.2 | 17 Aug 2026 | Rule and synthetic validation alignment. |
| 0.3 | 17 Aug 2026 | Phase 4A PostgreSQL persistence, durable API, storage, lifecycle, and Phase 4B sequencing. |

# Phase 4B Product Alignment

Phase 4B delivers verbatim raw row lineage and canonical fact normalization. Every imported Excel row is stored verbatim, and normalized into canonical WBS, budget, cost, commitment, schedule, and progress fact tables, with each fact retaining a direct foreign-key link to its raw row.

## Scope delivered in Phase 4B

Verbatim raw row ingestion with sheet name and row number preservation.

Canonical fact normalization for all six domains with raw_row_id foreign-key lineage.

Import batches and column mapping metadata tables.

Automated raw row extraction and normalization pipeline in the application service.

Reversible Alembic migration 20260821_0002.

## Change Log v0.4

| Version | Date | Change |
| --- | --- | --- |
| 0.1 | 17 Aug 2026 | Initial MVP blueprint. |
| 0.2 | 17 Aug 2026 | Rule and synthetic validation alignment. |
| 0.3 | 17 Aug 2026 | Phase 4A PostgreSQL persistence, durable API, storage, lifecycle, and Phase 4B sequencing. |
| 0.4 | 20 Aug 2026 | Phase 4B raw-row lineage, canonical fact normalization, and import batch tracking. |

# Phase 5B & 5C Product Alignment

Phase 5B and 5C deliver API hardening (cursor-based pagination, request idempotency) and deterministic project health scoring derived from finding severity penalties across Cost (30%), Schedule (30%), Progress (25%), and Data Quality (15%).

## Scope delivered in Phase 5B & 5C

Cursor pagination metadata on all list endpoints (projects, runs, findings).

X-Idempotency-Key support preventing redundant analysis execution.

Deterministic health scoring engine with transparent score breakdown and key finding drivers.

Standardized score bands: Healthy (80-100), Needs Attention (60-79), At Risk (40-59), Critical (0-39).

Health snapshot persistence and trend endpoints: GET /v1/analysis-runs/{run_id}/health and GET /v1/projects/{project_id}/health-trend.

Alembic migration 20260822_0003 for health_snapshots.

## Change Log v0.5

| Version | Date | Change |
| --- | --- | --- |
| 0.1 | 17 Aug 2026 | Initial MVP blueprint. |
| 0.2 | 17 Aug 2026 | Rule and synthetic validation alignment. |
| 0.3 | 17 Aug 2026 | Phase 4A PostgreSQL persistence, durable API, storage, lifecycle, and Phase 4B sequencing. |
| 0.4 | 20 Aug 2026 | Phase 4B raw-row lineage, canonical fact normalization, and import batch tracking. |
| 0.5 | 20 Aug 2026 | Phase 5A structured logging, Phase 5B pagination & idempotency, Phase 5C health scoring engine. |

# Phase 4C Product Alignment

Phase 4C implements production-grade authentication and Role-Based Access Control (RBAC). The temporary X-Organization-ID header is augmented with JWT Bearer tokens, salted bcrypt password hashing, and user/membership tables.

## Scope delivered in Phase 4C

Users table with bcrypt password hashing and status enforcement.

Organization members and project members tables for multi-tenant role management.

Role hierarchy: org_admin, org_member, org_viewer, project_manager, project_member, project_viewer.

JWT access and refresh token lifecycle with Authorization: Bearer support.

Auth endpoints: POST /v1/auth/register and POST /v1/auth/login.

Alembic migration 20260904_0004 for users, organization_members, and project_members.

## Change Log v0.6

| Version | Date | Change |
| --- | --- | --- |
| 0.1 | 17 Aug 2026 | Initial MVP blueprint. |
| 0.2 | 17 Aug 2026 | Rule and synthetic validation alignment. |
| 0.3 | 17 Aug 2026 | Phase 4A PostgreSQL persistence, durable API, storage, lifecycle, and Phase 4B sequencing. |
| 0.4 | 20 Aug 2026 | Phase 4B raw-row lineage, canonical fact normalization, and import batch tracking. |
| 0.5 | 20 Aug 2026 | Phase 5A structured logging, Phase 5B pagination & idempotency, Phase 5C health scoring engine. |
| 0.6 | 20 Aug 2026 | Phase 4C JWT authentication, bcrypt password hashing, and RBAC membership controls. |

# Phase 6 Product Alignment

Phase 6 delivers the AI Intelligence Layer. Guided by the principle 'Deterministic engine calculates, AI explains', the AI assistant uses controlled query tools grounded in canonical facts and findings with safety guardrails.

## Scope delivered in Phase 6

Controlled database query tools: get_project_health, get_top_cost_drivers, get_delayed_activities, get_finding_evidence.

AI safety guardrails (PRD §14.3) and structured response sanitization.

Deterministic grounded ProjectAIAssistant for answering health, cost, schedule, and evidence inquiries.

AI conversation and message history persistence (ai_conversations and ai_messages tables).

AI endpoints: POST /v1/projects/{project_id}/ai/ask, GET /v1/projects/{project_id}/ai/conversations, GET /v1/ai/conversations/{conversation_id}/messages.

Alembic migration 20260905_0005 for ai_conversations and ai_messages.

## Change Log v0.7

| Version | Date | Change |
| --- | --- | --- |
| 0.1 | 17 Aug 2026 | Initial MVP blueprint. |
| 0.2 | 17 Aug 2026 | Rule and synthetic validation alignment. |
| 0.3 | 17 Aug 2026 | Phase 4A PostgreSQL persistence, durable API, storage, lifecycle, and Phase 4B sequencing. |
| 0.4 | 20 Aug 2026 | Phase 4B raw-row lineage, canonical fact normalization, and import batch tracking. |
| 0.5 | 20 Aug 2026 | Phase 5A structured logging, Phase 5B pagination & idempotency, Phase 5C health scoring engine. |
| 0.6 | 20 Aug 2026 | Phase 4C JWT authentication, bcrypt password hashing, and RBAC membership controls. |
| 0.7 | 20 Aug 2026 | Phase 6 AI Intelligence Layer, safety guardrails, controlled tools, and audit assistant endpoints. |

# Phase 7 Production Readiness Alignment

Phase 7 establishes production hardening and deployment engineering standards for ControlCheck AI, ensuring container security, database resilience, cloud storage options, and automated CI/CD validation.

## Scope delivered in Phase 7

Multi-stage production Dockerfile with non-root security context (UID 10001).

Production Docker Compose setup (docker-compose.prod.yml) with PostgreSQL health checks.

Container liveness (/health/live) and database readiness (/health/ready) probes.

CORS middleware with configurable domain whitelist (CONTROLCHECK_CORS_ORIGINS).

S3 / MinIO cloud object storage backend implementation (S3FileStorage).

Automated GitHub Actions CI pipeline (.github/workflows/ci.yml).

Comprehensive Production Runbook (docs/PRODUCTION_RUNBOOK.md).

## Change Log v0.8

| Version | Date | Change |
| --- | --- | --- |
| 0.1 | 17 Aug 2026 | Initial MVP blueprint. |
| 0.2 | 17 Aug 2026 | Rule and synthetic validation alignment. |
| 0.3 | 17 Aug 2026 | Phase 4A PostgreSQL persistence, durable API, storage, lifecycle, and Phase 4B sequencing. |
| 0.4 | 20 Aug 2026 | Phase 4B raw-row lineage, canonical fact normalization, and import batch tracking. |
| 0.5 | 20 Aug 2026 | Phase 5A structured logging, Phase 5B pagination & idempotency, Phase 5C health scoring engine. |
| 0.6 | 20 Aug 2026 | Phase 4C JWT authentication, bcrypt password hashing, and RBAC membership controls. |
| 0.7 | 20 Aug 2026 | Phase 6 AI Intelligence Layer, safety guardrails, controlled tools, and audit assistant endpoints. |
| 0.8 | 20 Aug 2026 | Phase 7 Production Readiness, containerization, CORS hardening, probes, CI/CD, and runbook. |

# Phase 8 Web Dashboard & AI Copilot Alignment

Phase 8 delivers an enterprise-grade, responsive Web Dashboard and interactive AI Audit Copilot interface integrated directly into the ControlCheck AI platform.

## Scope delivered in Phase 8

Interactive Single-Page Application (SPA) dashboard served directly from FastAPI at root /.

Executive Circular SVG Health Gauge visualizing score (0-100) and score bands (Healthy, Needs Attention, At Risk, Critical).

Domain Score Breakdown Cards for Cost (30%), Schedule (30%), Progress (25%), and Data Quality (15%).

Drag & Drop project Excel workbook uploader (.xlsx) with instant client-side rendering.

Interactive Findings Explorer with category filters (Cost, Schedule, Progress, DQ) and real-time search.

Findings detail modal showcasing verbatim source sheet/row evidence, impact, and recommendations.

Interactive AI Audit Copilot chat sidebar integrated with /v1/projects/{project_id}/ai/ask and quick query chips.

## Change Log v0.9

| Version | Date | Change |
| --- | --- | --- |
| 0.1 | 17 Aug 2026 | Initial MVP blueprint. |
| 0.2 | 17 Aug 2026 | Rule and synthetic validation alignment. |
| 0.3 | 17 Aug 2026 | Phase 4A PostgreSQL persistence, durable API, storage, lifecycle, and Phase 4B sequencing. |
| 0.4 | 20 Aug 2026 | Phase 4B raw-row lineage, canonical fact normalization, and import batch tracking. |
| 0.5 | 20 Aug 2026 | Phase 5A structured logging, Phase 5B pagination & idempotency, Phase 5C health scoring engine. |
| 0.6 | 20 Aug 2026 | Phase 4C JWT authentication, bcrypt password hashing, and RBAC membership controls. |
| 0.7 | 20 Aug 2026 | Phase 6 AI Intelligence Layer, safety guardrails, controlled tools, and audit assistant endpoints. |
| 0.8 | 20 Aug 2026 | Phase 7 Production Readiness, containerization, CORS hardening, probes, CI/CD, and runbook. |
| 0.9 | 20 Aug 2026 | Phase 8 Web Dashboard, Executive Health Gauge, Findings Explorer, and AI Copilot Chat. |

# Phase 9 Smart Flexible Ingestion & Universal Auto-Mapper Alignment

Phase 9 delivers universal file compatibility for ControlCheck AI, enabling seamless ingestion of custom ERP spreadsheets, SAP exports, Primavera P6 exports, and Indonesian column conventions.

## Scope delivered in Phase 9

Dual-mode ingestion: Standard exact schema parser with graceful automated fallback to Smart Flexible Auto-Mapper.

Fuzzy sheet name detection supporting multilingual aliases (e.g., 'Anggaran RAB', 'Realisasi Biaya', 'Jadwal Proyek', 'Kurva S').

Comprehensive column synonym dictionary mapping 50+ localized ERP headers into canonical fact models.

Adaptive metadata synthesization (automatic project_id, data_date, and currency defaults when metadata sheet is omitted).

Robust numeric, percentage, and date parsing supporting IDR currency symbols, dot/comma decimals, and international date formats.

Zero-configuration drag & drop on Web UI command center for arbitrary project spreadsheets.

## Change Log v1.0

| Version | Date | Change |
| --- | --- | --- |
| 0.1 | 17 Aug 2026 | Initial MVP blueprint. |
| 0.2 | 17 Aug 2026 | Rule and synthetic validation alignment. |
| 0.3 | 17 Aug 2026 | Phase 4A PostgreSQL persistence, durable API, storage, lifecycle, and Phase 4B sequencing. |
| 0.4 | 20 Aug 2026 | Phase 4B raw-row lineage, canonical fact normalization, and import batch tracking. |
| 0.5 | 20 Aug 2026 | Phase 5A structured logging, Phase 5B pagination & idempotency, Phase 5C health scoring engine. |
| 0.6 | 20 Aug 2026 | Phase 4C JWT authentication, bcrypt password hashing, and RBAC membership controls. |
| 0.7 | 20 Aug 2026 | Phase 6 AI Intelligence Layer, safety guardrails, controlled tools, and audit assistant endpoints. |
| 0.8 | 20 Aug 2026 | Phase 7 Production Readiness, containerization, CORS hardening, probes, CI/CD, and runbook. |
| 0.9 | 20 Aug 2026 | Phase 8 Web Dashboard, Executive Health Gauge, Findings Explorer, and AI Copilot Chat. |
| 1.0 | 20 Aug 2026 | Phase 9 Smart Flexible Ingestion, Multilingual Sheet/Header Auto-Mapper, and General Availability. |

# Phase 10 Public Beta Cloud Deployment & Usage Validation Alignment

The public-beta cloud architecture is browser → Vercel frontend → Render Free FastAPI → Supabase Free PostgreSQL plus private Cloudflare R2 Standard object storage.

## Hosted data flow

register/login → create project → upload workbook → persist workbook in R2 → canonical ingestion and deterministic analysis on Render → persist run/findings/evidence in Supabase → display results in Vercel.

## Public-beta success criteria

hosted register-to-findings flow passes.

uploaded files and results persist across Render restart/cold start.

no secrets appear in source/logs/docs.

registrations, active users, projects, workbook uploads, and completed analysis runs are measurable from persisted records.

## Free-tier constraints and upgrade triggers

Render cold start after idle.

Supabase Free may pause after low activity and has limited capacity/no managed downloadable backups.

R2 Standard free allowance is used and the bucket remains private.

Upgrade when user experience is materially affected by cold starts, Supabase database approaches 400 MB, R2 approaches 8 GB, or usage becomes routine enough to justify an always-on backend.

## Deferred non-goals

full authentication/RBAC hardening, payment/subscription, enterprise SSO, and production-scale HA/DR remain deferred.

## Change Log v1.1

| Version | Date | Change |
| --- | --- | --- |
| 1.1 | 26 Aug 2026 | public-beta cloud architecture and usage validation. |