# ControlCheck AI

Control Rule Catalogue v0.1

MVP deterministic control rules | 20 rules | 5 control domains

Purpose. This catalogue defines the first production-oriented rule set for ControlCheck AI. The rule engine must calculate deterministic findings from canonical project data; LLM reasoning explains and prioritizes findings but does not replace rule calculations.

# 1. Rule Set Summary

| Domain | Count | Rule IDs | Business intent |
| --- | --- | --- | --- |
| Data Quality | 5 | DQ-001 to DQ-005 | Ensure the data can be trusted before project-control analysis. |
| Cost | 5 | CST-001 to CST-005 | Detect current and emerging cost exposure. |
| Schedule | 5 | SCH-001 to SCH-005 | Detect slippage, critical-path risk, and float issues. |
| Progress | 2 | PRG-001 to PRG-002 | Detect progress inconsistencies and performance gaps. |
| Cross-domain | 3 | CST-006, PRG-003, XDOM-001 | Detect interactions between spend, progress, and schedule. |

# 2. Evaluation Principles

Rules are deterministic and testable. The same input data and analysis date must produce the same finding set.

Every material finding must carry evidence references to source rows and canonical records whenever technically possible.

Thresholds are configuration, not hard-coded business logic. Each rule should expose project-level overrides.

Findings must be idempotent within the same project, rule version, and reporting cut-off; repeated runs must not create uncontrolled duplicates.

LLM output is advisory. It can summarize evidence, propose root causes, and recommend actions, but it cannot invent metrics or silently alter rule results.

# 3. Severity Model

| Severity | Meaning | UI treatment |
| --- | --- | --- |
| Critical | Immediate management review. Material cost/schedule exposure or severe data integrity issue. | Red |
| Warning | Requires project-control review and likely action, but impact is not yet confirmed material. | Amber |
| Observation | Useful signal or data hygiene issue. No direct escalation required unless repeated. | Blue/Neutral |

# 4. Detailed Rule Catalogue

## 01. DQ-001 — Missing WBS Reference

| Field | Specification |
| --- | --- |
| Category | data_quality |
| Default severity | warning |
| Objective | Detect budget, cost, schedule, or progress records that cannot be tied to a project WBS node. |
| Inputs | budget_records, cost_records, schedule_activities, progress_records, wbs_nodes |
| Detection logic | For each domain record, wbs_node_id must resolve to an active WBS node for the same project. Missing or unresolved WBS creates a finding. |
| Threshold | Any unresolved WBS record; configurable minimum count = 1. |
| Evidence | Source dataset, original row number, source WBS value, project code. |
| Finding template | {dataset} contains {count} records without a valid WBS reference. |
| Impact | Weak traceability; cost/progress/schedule rollups may be incomplete or misleading. |
| Recommendation | Map the source WBS to the canonical WBS tree or correct the source record before analysis. |
| False-positive handling | Allow approved non-WBS records to be excluded by dataset mapping rule. |
| Acceptance criteria | A test file with 5 unresolved WBS records produces exactly 5 evidence rows and 1 grouped finding. |

## 02. DQ-002 — Duplicate Cost Transaction

| Field | Specification |
| --- | --- |
| Category | data_quality |
| Default severity | warning |
| Objective | Detect probable duplicate cost transactions introduced by repeated rows or repeated file imports. |
| Inputs | cost_records, raw_rows |
| Detection logic | Build a normalized duplicate key from project_id + transaction_date + vendor_code/name + po_number + document_number + amount + normalized description. Group count > 1. |
| Threshold | Duplicate group count >= 2; confidence increases when document_number or PO matches exactly. |
| Evidence | Duplicate record IDs, source row numbers, duplicate key fields, amounts. |
| Finding template | {count} probable duplicate cost transactions detected across {groups} duplicate groups. |
| Impact | Can inflate actual cost, commitments, vendor exposure, and forecasts. |
| Recommendation | Verify source duplicates against invoice/document number and remove or mark repeated rows. |
| False-positive handling | Permit legitimate split postings where document number differs or accounting status indicates separate posting. |
| Acceptance criteria | Known duplicate pair is detected as one group; legitimate split pair is not grouped when document numbers differ. |

## 03. DQ-003 — Contradictory Date or Progress Values

| Field | Specification |
| --- | --- |
| Category | data_quality |
| Default severity | warning |
| Objective | Identify records with internally inconsistent dates or progress values before control calculations. |
| Inputs | raw_rows, schedule_activities, progress_records |
| Detection logic | Flag schedule rows where finish < start, actual finish < actual start, progress outside 0..1, or progress period is earlier than project planned start when disallowed. |
| Threshold | Any contradictory record; ingestion should reject hard-invalid values and retain evidence. |
| Evidence | Dataset, row number, offending fields, validation message. |
| Finding template | {count} records contain contradictory date/progress values. |
| Impact | Can distort delay, SPI, progress, and health calculations. |
| Recommendation | Correct source values and re-import the affected dataset. |
| False-positive handling | Project-specific exceptions must be explicitly configured rather than silently ignored. |
| Acceptance criteria | Each invalid record is traceable to the original row and receives a deterministic validation reason. |

## 04. DQ-004 — Orphan WBS Reference

| Field | Specification |
| --- | --- |
| Category | data_quality |
| Default severity | critical |
| Objective | Detect records referencing a WBS code that does not exist in the project canonical WBS tree. |
| Inputs | raw_rows, wbs_nodes and domain datasets |
| Detection logic | Source WBS value is present but no matching canonical wbs_nodes row exists for the same project. |
| Threshold | Any orphan WBS; severity critical when orphaned amount exceeds 1% of project budget. |
| Evidence | Source WBS, project, affected records, aggregated amount/progress. |
| Finding template | WBS {source_wbs} is not mapped to the project WBS tree; {count} records are affected. |
| Impact | Rollup leakage; affected costs/progress may disappear from management totals. |
| Recommendation | Create a mapping or add the missing WBS node after project-control approval. |
| False-positive handling | None for active analysis; retired WBS can be supported through explicit alias/mapping. |
| Acceptance criteria | A missing WBS with material cost is critical and appears in the evidence view. |

## 05. DQ-005 — Vendor Identity Inconsistency

| Field | Specification |
| --- | --- |
| Category | data_quality |
| Default severity | observation |
| Objective | Detect the same vendor appearing under multiple codes/names that can fragment spend analysis. |
| Inputs | cost_records |
| Detection logic | Normalize vendor_name. Flag a normalized name mapped to >1 vendor_code, or one vendor_code mapped to materially different normalized names. |
| Threshold | At least 2 distinct identities; warning when affected spend > 2% of project actual cost. |
| Evidence | Vendor codes, names, transaction count, total amount. |
| Finding template | Vendor identity inconsistency found for {normalized_vendor}; {identity_count} identities represent {amount}. |
| Impact | Vendor concentration and cost-driver analysis can be understated or duplicated. |
| Recommendation | Create a canonical vendor mapping and standardize future imports. |
| False-positive handling | Joint ventures or legal entities may legitimately have separate codes; permit approved mapping exceptions. |
| Acceptance criteria | Known alias set is grouped together while explicitly distinct legal entities remain separate when configured. |

## 06. CST-001 — Actual Cost Exceeds Budget

| Field | Specification |
| --- | --- |
| Category | cost |
| Default severity | critical |
| Objective | Detect WBS-level actual cost overruns against approved budget. |
| Inputs | cost_records where cost_type=actual, budget_records |
| Detection logic | Aggregate actual amount and approved budget by project + WBS. Variance = actual - approved_budget. Trigger when variance > 0. |
| Threshold | Default: any positive variance; severity critical when variance_pct >= 10% or variance_amount >= configurable materiality. |
| Evidence | Budget record(s), all contributing actual transactions, WBS rollup. |
| Finding template | WBS {wbs} actual cost exceeds approved budget by {variance_amount} ({variance_pct}). |
| Impact | Confirmed cost overrun at current reporting cut-off. |
| Recommendation | Review quantity/price variance, commitments, change orders, and coding before escalation. |
| False-positive handling | Approved revised budget must replace the prior baseline used for the check. |
| Acceptance criteria | Synthetic WBS with budget 100 and actual 124 returns variance 24 and 24%. |

## 07. CST-002 — Actual + Commitment Exceeds Budget

| Field | Specification |
| --- | --- |
| Category | cost |
| Default severity | critical |
| Objective | Detect likely future overrun where actual plus open commitment already exceeds approved budget. |
| Inputs | cost_records where cost_type in (actual, commitment), budget_records |
| Detection logic | Exposure = actual + commitment. Trigger when exposure > approved_budget. |
| Threshold | Warning when > 100%; critical when >= 110% or materiality threshold is exceeded. |
| Evidence | Budget, actual transactions, commitment transactions, PO numbers. |
| Finding template | WBS {wbs} has committed exposure of {exposure} versus budget {budget}. |
| Impact | Forward-looking overrun exposure even if actual spend has not yet exceeded budget. |
| Recommendation | Review open PO values, remaining scope, pending variations, and potential decommitment. |
| False-positive handling | Exclude commitments already cancelled/closed or fully reversed. |
| Acceptance criteria | Open commitment pushes exposure from 98% to 106%; rule returns warning with correct evidence. |

## 08. CST-003 — Cost Spike vs Recent Run Rate

| Field | Specification |
| --- | --- |
| Category | cost |
| Default severity | warning |
| Objective | Detect sudden cost acceleration that warrants project-control review. |
| Inputs | cost_records actual by month/period |
| Detection logic | For each WBS, current_period_cost > trailing_3_period_average * (1 + spike_threshold). Only evaluate when at least 3 prior comparable periods exist. |
| Threshold | Default spike_threshold = 30%; configurable minimum absolute amount = 1% of BAC or project materiality. |
| Evidence | Current period cost, three-period baseline, ratio, underlying transactions. |
| Finding template | WBS {wbs} cost increased {increase_pct} versus trailing 3-period average. |
| Impact | Potential acceleration, bulk procurement, coding issue, or emerging cost risk. |
| Recommendation | Inspect high-value transactions, PO releases, procurement timing, and coding changes. |
| False-positive handling | Planned bulk purchases can be tagged as expected events. |
| Acceptance criteria | A 40% spike above three-period average is detected; 20% spike is not. |

## 09. CST-004 — Vendor Concentration Risk

| Field | Specification |
| --- | --- |
| Category | cost |
| Default severity | warning |
| Objective | Detect excessive dependence on one vendor within project spend. |
| Inputs | cost_records actual by vendor |
| Detection logic | vendor_share = vendor_actual / project_actual for selected period or cumulative view. |
| Threshold | Default warning >= 40%; critical >= 60% when project configuration enables concentration monitoring. |
| Evidence | Vendor total, project total, share, top transactions. |
| Finding template | Vendor {vendor} represents {share} of project actual cost. |
| Impact | Commercial concentration and change/claim dependency may be high. |
| Recommendation | Review scope dependency, outstanding commitments, commercial exposure, and alternatives. |
| False-positive handling | Single-source contracts can be explicitly marked expected. |
| Acceptance criteria | Vendor with 45% share creates warning; 35% does not. |

## 10. CST-005 — High-Value Transaction Outlier

| Field | Specification |
| --- | --- |
| Category | cost |
| Default severity | observation |
| Objective | Surface unusually large individual transactions relative to WBS or project budget. |
| Inputs | cost_records actual, budget_records |
| Detection logic | transaction_share = transaction_amount / WBS_budget. Trigger when share exceeds threshold. |
| Threshold | Default >= 5% of WBS budget or >= 2% of project budget, with configurable absolute materiality floor. |
| Evidence | Transaction record, budget context, PO/document number, vendor. |
| Finding template | Transaction {document} represents {share} of WBS budget and requires review. |
| Impact | Large transactions may contain quantity, price, coding, or timing anomalies. |
| Recommendation | Verify supporting document, approved scope, coding, and period allocation. |
| False-positive handling | Known milestone or advance-payment transactions can be tagged expected. |
| Acceptance criteria | Transaction at 6% of WBS budget is surfaced; 3% is not unless project materiality overrides. |

## 11. CST-006 — High Cost with Low Progress

| Field | Specification |
| --- | --- |
| Category | cross_domain |
| Default severity | critical |
| Objective | Detect WBSs where spend is materially advanced while physical progress remains materially low. |
| Inputs | cost_records actual, budget_records, progress_records |
| Detection logic | For same WBS and latest period: cost_pct = actual_to_date / budget; progress_pct = actual_progress. Trigger when cost_pct >= 80% AND progress_pct <= 50%. |
| Threshold | Default 80% cost vs <=50% progress; configurable by project type. |
| Evidence | Budget, actual-to-date, latest progress, period history, major transactions. |
| Finding template | WBS {wbs} has consumed {cost_pct} of budget while progress is {progress_pct}. |
| Impact | Potential quantity/price issue, low productivity, front-loaded procurement, or scope accounting risk. |
| Recommendation | Perform cost-to-progress reconciliation and validate quantity, productivity, and procurement timing. |
| False-positive handling | Front-loaded procurement packages should be tagged as expected. |
| Acceptance criteria | 80% cost / 45% progress triggers; 75% / 45% does not. |

## 12. SCH-001 — Overdue Activity

| Field | Specification |
| --- | --- |
| Category | schedule |
| Default severity | warning |
| Objective | Detect incomplete activities whose baseline finish is before the analysis date. |
| Inputs | schedule_activities |
| Detection logic | actual_progress < 1 AND baseline_finish < analysis_date AND status not in completed/cancelled. |
| Threshold | Default any overdue activity; critical when activity is critical_flag=true or overdue_days >= 14. |
| Evidence | Activity, baseline finish, actual progress/status, analysis date, overdue days. |
| Finding template | Activity {activity} is overdue by {days} days with progress {progress}. |
| Impact | Schedule slippage and potential downstream impact. |
| Recommendation | Confirm actual field status, recovery plan, and downstream dependencies. |
| False-positive handling | Approved baseline changes must update the active baseline or be versioned explicitly. |
| Acceptance criteria | Activity 10 days overdue creates warning; 14 days or critical activity creates critical. |

## 13. SCH-002 — Baseline Finish Slippage

| Field | Specification |
| --- | --- |
| Category | schedule |
| Default severity | warning |
| Objective | Detect completed activities that finished later than baseline. |
| Inputs | schedule_activities |
| Detection logic | actual_finish > baseline_finish. slippage_days = actual_finish - baseline_finish. |
| Threshold | Default warning >= 7 days; critical >= 14 days or project-configured threshold. |
| Evidence | Activity baseline and actual dates, slippage days. |
| Finding template | Activity {activity} finished {slippage_days} days later than baseline. |
| Impact | Evidence of schedule variance and possible milestone impact. |
| Recommendation | Capture delay reason, responsibility, and lesson/action if material. |
| False-positive handling | Approved rebaseline should be compared using the correct baseline version. |
| Acceptance criteria | 8-day slippage is warning; 15-day slippage is critical. |

## 14. SCH-003 — Critical Activity Delay

| Field | Specification |
| --- | --- |
| Category | schedule |
| Default severity | critical |
| Objective | Prioritize delayed activities on the critical path. |
| Inputs | schedule_activities |
| Detection logic | critical_flag=true AND (overdue OR actual_finish > baseline_finish OR total_float_days < 0). |
| Threshold | Any critical activity meeting delay condition. |
| Evidence | Activity critical flag, dates, float, progress, status. |
| Finding template | Critical activity {activity} is delayed/at risk and may affect project completion. |
| Impact | Potential direct impact to project completion or major milestone. |
| Recommendation | Escalate recovery plan, predecessors/successors, resources, and mitigation actions. |
| False-positive handling | Critical flag must reflect the approved current schedule version. |
| Acceptance criteria | A critical activity 1 day overdue creates a critical finding regardless of amount. |

## 15. SCH-004 — Activity Progress Lag

| Field | Specification |
| --- | --- |
| Category | schedule |
| Default severity | warning |
| Objective | Detect activities whose actual progress materially trails planned progress. |
| Inputs | schedule_activities |
| Detection logic | progress_lag = planned_progress - actual_progress. Trigger when lag exceeds threshold. |
| Threshold | Default >= 10 percentage points; critical >= 20 points for critical activities. |
| Evidence | Activity planned vs actual progress, dates, status. |
| Finding template | Activity {activity} is {lag_pp} percentage points behind plan. |
| Impact | Early signal of schedule recovery requirement. |
| Recommendation | Validate field progress and determine root cause and recovery action. |
| False-positive handling | Progress methodology changes must be reflected before analysis. |
| Acceptance criteria | 11 pp lag triggers warning; 9 pp does not. |

## 16. SCH-005 — Negative Total Float

| Field | Specification |
| --- | --- |
| Category | schedule |
| Default severity | critical |
| Objective | Detect schedule activities with negative total float. |
| Inputs | schedule_activities |
| Detection logic | total_float_days < 0. |
| Threshold | Any negative float. |
| Evidence | Activity, float value, schedule version/date. |
| Finding template | Activity {activity} has {float_days} days negative float. |
| Impact | Activity requires schedule recovery or network review to protect milestones. |
| Recommendation | Review driving path, constraints, calendars, and recovery options. |
| False-positive handling | External interface constraints may be intentionally modeled; retain evidence and approval notes. |
| Acceptance criteria | Float -1 creates critical finding; float 0 does not. |

## 17. PRG-001 — WBS Progress Lag

| Field | Specification |
| --- | --- |
| Category | progress |
| Default severity | warning |
| Objective | Detect WBS-level actual progress materially behind plan for the latest reporting period. |
| Inputs | progress_records |
| Detection logic | progress_lag = planned_progress - actual_progress for latest period per WBS. |
| Threshold | Default >= 10 percentage points; critical >= 20 points or when linked to critical schedule activities. |
| Evidence | Latest progress record, prior periods, WBS. |
| Finding template | WBS {wbs} is {lag_pp} percentage points behind plan. |
| Impact | Project delivery risk if gap persists. |
| Recommendation | Investigate workfront constraints, productivity, materials, resources, and schedule logic. |
| False-positive handling | Milestone-weighted or earned-value methodologies should be configured consistently. |
| Acceptance criteria | 12 pp gap creates warning; 8 pp gap does not. |

## 18. PRG-002 — Progress Above 100 Percent

| Field | Specification |
| --- | --- |
| Category | progress |
| Default severity | warning |
| Objective | Detect source progress values that exceed logical maximums. |
| Inputs | raw_rows, progress_records, schedule_activities |
| Detection logic | Flag any source actual_progress or planned_progress > 1.0, including values encoded as 100+ percent after normalization. |
| Threshold | Any value > 100%. |
| Evidence | Original source value, normalized value, row number. |
| Finding template | Progress value {value} for {wbs/activity} exceeds 100%. |
| Impact | Can distort project progress and health calculations. |
| Recommendation | Correct source encoding and re-import. |
| False-positive handling | None in canonical percentage field; alternate units must be transformed during mapping. |
| Acceptance criteria | 101% is flagged; 100% is valid. |

## 19. PRG-003 — Cost Rising While Progress Flat

| Field | Specification |
| --- | --- |
| Category | cross_domain |
| Default severity | critical |
| Objective | Detect WBS periods where cost continues to rise but physical progress barely changes. |
| Inputs | cost_records actual by period, progress_records |
| Detection logic | For latest two comparable periods: cost_change_pct >= 20% AND progress_change_pp <= 2 points. |
| Threshold | Default cost +20% and progress change <=2 pp; materiality floor applies. |
| Evidence | Two-period cost totals, progress values, top transactions. |
| Finding template | WBS {wbs} cost increased {cost_change_pct} while progress changed only {progress_change_pp}. |
| Impact | Possible productivity loss, stalled workfront, advance procurement, or coding issue. |
| Recommendation | Reconcile cost to installed quantities/progress and investigate top spend drivers. |
| False-positive handling | Advance procurement and known front-loaded packages can be tagged expected. |
| Acceptance criteria | Cost +25% with progress +1 pp triggers; cost +15% does not. |

## 20. XDOM-001 — Schedule Delay with High Cost Exposure

| Field | Specification |
| --- | --- |
| Category | cross_domain |
| Default severity | critical |
| Objective | Prioritize WBSs where schedule delay and cost exposure coexist. |
| Inputs | schedule_activities, budget_records, cost_records, progress_records |
| Detection logic | Trigger when WBS has overdue/critical delayed activity AND cost_exposure_pct >= 80% of budget OR actual_cost > 90% of budget. |
| Threshold | Default schedule delay + >=80% exposure; critical when exposure >=100%. |
| Evidence | Delayed activities, budget, actual/commitment exposure, progress. |
| Finding template | WBS {wbs} combines schedule delay with {exposure_pct} cost exposure. |
| Impact | Higher probability of time and cost overrun occurring together. |
| Recommendation | Escalate WBS as integrated cost-schedule risk; review recovery, remaining budget, and forecast. |
| False-positive handling | Planned front-loaded work must be marked expected and still monitored. |
| Acceptance criteria | Delayed activity + 85% exposure creates critical finding; delayed + 60% exposure does not. |

# 5. Control Rule Runtime Contract

Every rule is stored in control_rules.expression as JSONB. The backend should compile this declarative expression into a safe evaluator rather than executing arbitrary Python supplied by users.

{
  "metric": "actual_to_date",
  "group_by": [
    "project_id",
    "wbs_node_id"
  ],
  "conditions": [
    {
      "field": "actual_to_date",
      "op": ">",
      "value": "approved_budget"
    }
  ],
  "threshold": {
    "type": "percent",
    "value": 10
  },
  "severity_map": {
    "warning": 0,
    "critical": 10
  },
  "evidence": [
    "budget_records",
    "cost_records"
  ]
}

# 6. Threshold Configuration

| Configuration key | Default | Rule | Meaning |
| --- | --- | --- | --- |
| spike_threshold_pct | 30 | CST-003 | Cost acceleration threshold vs trailing average. |
| vendor_concentration_pct | 40 | CST-004 | Vendor share warning threshold. |
| high_value_wbs_pct | 5 | CST-005 | Single transaction share of WBS budget. |
| low_progress_pct | 50 | CST-006 | Upper progress threshold for high-cost/low-progress. |
| high_cost_pct | 80 | CST-006 | Cost consumed threshold for high-cost/low-progress. |
| overdue_days | 14 | SCH-001 | Critical overdue threshold. |
| slippage_warning_days | 7 | SCH-002 | Schedule finish slippage warning threshold. |
| slippage_critical_days | 14 | SCH-002 | Schedule finish slippage critical threshold. |
| activity_progress_lag_pp | 10 | SCH-004 | Activity planned-vs-actual progress warning gap. |
| wbs_progress_lag_pp | 10 | PRG-001 | WBS planned-vs-actual progress warning gap. |
| cost_rise_pct | 20 | PRG-003 | Cost increase threshold for flat-progress detection. |
| progress_change_pp | 2 | PRG-003 | Maximum progress change considered flat. |
| exposure_pct | 80 | XDOM-001 | Cost exposure threshold when schedule delay exists. |

# 7. Evidence Requirements

Every finding stores evidence JSON and should preferably reference evidence_records for normalized links.

At minimum, evidence must identify project, rule, WBS/activity where applicable, source dataset, source file, and original row number.

Aggregated metrics must store enough information to reproduce the calculation: numerator, denominator, period, and threshold used.

For cost findings, include the contributing transaction IDs or raw row IDs when the set is not excessively large. Large evidence sets may be summarized with a downloadable detail view.

# 8. Test Data Strategy

The next engineering artifact should be a synthetic project dataset deliberately seeded with known violations. Each rule needs at least one positive case and one near-boundary negative case.

| Rule | Positive test fixture | Expected |
| --- | --- | --- |
| DQ-001 | 5 records with missing WBS | 5 evidence rows |
| CST-001 | Budget 100 / actual 124 | 24 overrun and 24% |
| CST-003 | Baseline average 100 / current 140 | 40% spike |
| SCH-003 | Critical activity overdue 1 day | Critical finding |
| PRG-003 | Cost +25% / progress +1 pp | Cross-domain finding |
| XDOM-001 | Delayed + 85% cost exposure | Critical integrated risk |

# 9. Implementation Order

Implement DQ-001..DQ-005 first so downstream calculations operate on trusted data.

Implement CST-001..CST-005 and SCH-001..SCH-005 next; these provide the first valuable dashboard signals.

Add PRG-001..PRG-002, then cross-domain rules CST-006, PRG-003, XDOM-001.

Only after deterministic findings pass the synthetic test suite should the AI reasoning layer be connected.

Every production release must record rule version changes and preserve historical finding calculations.

# 10. Definition of Done for Rule Engine v0.1

20 rules implemented behind a common rule runtime contract.

Rule thresholds configurable by project without changing code.

All rules return deterministic findings with severity, metric, and evidence.

Synthetic dataset produces expected findings for positive and negative test cases.

Rule execution records timing and counts in control_rule_runs.

Finding results are auditable back to source file and row where applicable.

Re-running the same input is idempotent for the same project, cut-off, rule version, and dataset snapshot.

No LLM is required for numeric calculation or threshold evaluation.