## Project_Info
CONTROL CHECK AI — SYNTHETIC PROJECT | VALUE
project_id | PRJ-CCAI-001
project_name | EPC Gas Compression Facility Expansion
client | PT Nusantara Energi
contractor | PT Delta EPC Indonesia
location | East Kalimantan, Indonesia
contract_type | Lump Sum Turnkey
currency | IDR
baseline_start | 2026-01-05
baseline_finish | 2026-12-18
data_date | 2026-08-15
project_status | Execution
purpose | Synthetic demo and rule-engine validation dataset for ControlCheck AI

## WBS
WBS
wbs_code | wbs_name | parent_wbs | discipline | level
1.0 | Engineering |  | ENG | 1
1.1 | Process & Mechanical Engineering | 1.0 | ENG | 2
1.2 | Civil & Structural Engineering | 1.0 | ENG | 2
2.0 | Procurement |  | PROC | 1
2.1 | Major Equipment | 2.0 | PROC | 2
2.2 | Bulk Materials | 2.0 | PROC | 2
3.0 | Construction |  | CONST | 1
3.1 | Civil Works | 3.0 | CONST | 2
3.2 | Mechanical Installation | 3.0 | CONST | 2
3.3 | Electrical & Instrumentation | 3.0 | CONST | 2
4.0 | Pre-Commissioning & Commissioning |  | COMM | 1
5.0 | Project Management & Indirect |  | PM | 1

## Budget
BUDGET
budget_id | wbs_code | cost_code | description | budget_amount | status | effective_date
BUD-001 | 1.1 | CC-11 | Approved budget for WBS 1.1 | 5000000000 | Approved | 2026-01-05
BUD-002 | 1.2 | CC-12 | Approved budget for WBS 1.2 | 4000000000 | Approved | 2026-01-05
BUD-003 | 2.1 | CC-21 | Approved budget for WBS 2.1 | 28000000000 | Approved | 2026-01-05
BUD-004 | 2.2 | CC-22 | Approved budget for WBS 2.2 | 16000000000 | Approved | 2026-01-05
BUD-005 | 3.1 | CC-31 | Approved budget for WBS 3.1 | 12000000000 | Approved | 2026-01-05
BUD-006 | 3.2 | CC-32 | Approved budget for WBS 3.2 | 18000000000 | Approved | 2026-01-05
BUD-007 | 3.3 | CC-33 | Approved budget for WBS 3.3 | 14000000000 | Approved | 2026-01-05
BUD-008 | 4.0 | CC-40 | Approved budget for WBS 4.0 | 5000000000 | Approved | 2026-01-05
BUD-009 | 5.0 | CC-50 | Approved budget for WBS 5.0 | 8000000000 | Approved | 2026-01-05

## Actual_Cost
ACTUAL COST
transaction_id | transaction_date | wbs_code | cost_code | vendor_id | vendor_name | po_number | description | actual_amount | status
ACT-0001 | 2026-01-23 | 1.1 | CC-11 | V006 | PT Survey Indo | PO-1001 | Invoice 1 | 164389000 | Posted
ACT-0002 | 2026-01-18 | 1.2 | CC-12 | V002 | PT Borneo Civil | PO-1002 | Invoice 2 | 146428000 | Posted
ACT-0003 | 2026-02-01 | 2.1 | CC-21 | V006 | PT Survey Indo | PO-1003 | Invoice 3 | 1507957000 | Posted
ACT-0004 | 2026-01-16 | 2.2 | CC-22 | V001 | PT Alpha Fabrication | PO-1004 | Invoice 4 | 781596000 | Posted
ACT-0005 | 2026-01-22 | 3.1 | CC-31 | V001 | PT Alpha Fabrication | PO-1005 | Invoice 5 | 387478000 | Posted
ACT-0006 | 2026-02-01 | 3.2 | CC-32 | V005 | PT Mekanika Utama | PO-1006 | Invoice 6 | 886211000 | Posted
ACT-0007 | 2026-02-01 | 3.3 | CC-33 | V002 | PT Borneo Civil | PO-1007 | Invoice 7 | 742476000 | Posted
ACT-0008 | 2026-02-02 | 4.0 | CC-40 | V004 | PT Prima Logistics | PO-1008 | Invoice 8 | 182573000 | Posted
ACT-0009 | 2026-01-15 | 5.0 | CC-50 | V003 | PT Kaltim Electrical | PO-1009 | Invoice 9 | 449181000 | Posted
ACT-0010 | 2026-02-24 | 1.1 | CC-11 | V002 | PT Borneo Civil | PO-1010 | Invoice 10 | 262190000 | Posted
ACT-0011 | 2026-02-24 | 1.2 | CC-12 | V003 | PT Kaltim Electrical | PO-1011 | Invoice 11 | 137397000 | Posted
ACT-0012 | 2026-02-17 | 2.1 | CC-21 | V001 | PT Alpha Fabrication | PO-1012 | Invoice 12 | 903229000 | Posted
ACT-0013 | 2026-03-05 | 2.2 | CC-22 | V003 | PT Kaltim Electrical | PO-1013 | Invoice 13 | 918664000 | Posted
ACT-0014 | 2026-02-28 | 3.1 | CC-31 | V003 | PT Kaltim Electrical | PO-1014 | Invoice 14 | 672851000 | Posted
ACT-0015 | 2026-02-26 | 3.2 | CC-32 | V005 | PT Mekanika Utama | PO-1015 | Invoice 15 | 599896000 | Posted
ACT-0016 | 2026-03-06 | 3.3 | CC-33 | V001 | PT Alpha Fabrication | PO-1016 | Invoice 16 | 665952000 | Posted
ACT-0017 | 2026-02-25 | 4.0 | CC-40 | V005 | PT Mekanika Utama | PO-1017 | Invoice 17 | 293409000 | Posted
ACT-0018 | 2026-02-16 | 5.0 | CC-50 | V005 | PT Mekanika Utama | PO-1018 | Invoice 18 | 284610000 | Posted
ACT-0019 | 2026-03-25 | 1.1 | CC-11 | V001 | PT Alpha Fabrication | PO-1019 | Invoice 19 | 256044000 | Posted
ACT-0020 | 2026-03-19 | 1.2 | CC-12 | V001 | PT Alpha Fabrication | PO-1020 | Invoice 20 | 230709000 | Posted
ACT-0021 | 2026-04-05 | 2.1 | CC-21 | V004 | PT Prima Logistics | PO-1021 | Invoice 21 | 1076109000 | Posted
ACT-0022 | 2026-03-27 | 2.2 | CC-22 | V003 | PT Kaltim Electrical | PO-1022 | Invoice 22 | 553416000 | Posted
ACT-0023 | 2026-04-05 | 3.1 | CC-31 | V002 | PT Borneo Civil | PO-1023 | Invoice 23 | 618070000 | Posted
ACT-0024 | 2026-03-21 | 3.2 | CC-32 | V001 | PT Alpha Fabrication | PO-1024 | Invoice 24 | 890479000 | Posted
ACT-0025 | 2026-03-21 | 3.3 | CC-33 | V005 | PT Mekanika Utama | PO-1025 | Invoice 25 | 748593000 | Posted
ACT-0026 | 2026-04-05 | 4.0 | CC-40 | V004 | PT Prima Logistics | PO-1026 | Invoice 26 | 209076000 | Posted
ACT-0027 | 2026-03-26 | 5.0 | CC-50 | V006 | PT Survey Indo | PO-1027 | Invoice 27 | 381853000 | Posted
ACT-0028 | 2026-04-16 | 1.1 | CC-11 | V001 | PT Alpha Fabrication | PO-1028 | Invoice 28 | 184008000 | Posted
ACT-0029 | 2026-04-17 | 1.2 | CC-12 | V003 | PT Kaltim Electrical | PO-1029 | Invoice 29 | 170155000 | Posted
ACT-0030 | 2026-05-03 | 2.1 | CC-21 | V002 | PT Borneo Civil | PO-1030 | Invoice 30 | 1668927000 | Posted
ACT-0031 | 2026-05-05 | 2.2 | CC-22 | V006 | PT Survey Indo | PO-1031 | Invoice 31 | 634495000 | Posted
ACT-0032 | 2026-05-05 | 3.1 | CC-31 | V004 | PT Prima Logistics | PO-1032 | Invoice 32 | 508253000 | Posted
ACT-0033 | 2026-04-19 | 3.2 | CC-32 | V004 | PT Prima Logistics | PO-1033 | Invoice 33 | 610723000 | Posted
ACT-0034 | 2026-05-02 | 3.3 | CC-33 | V002 | PT Borneo Civil | PO-1034 | Invoice 34 | 755995000 | Posted
ACT-0035 | 2026-04-28 | 4.0 | CC-40 | V003 | PT Kaltim Electrical | PO-1035 | Invoice 35 | 270336000 | Posted
ACT-0036 | 2026-04-22 | 5.0 | CC-50 | V005 | PT Mekanika Utama | PO-1036 | Invoice 36 | 339840000 | Posted
ACT-0037 | 2026-05-17 | 1.1 | CC-11 | V002 | PT Borneo Civil | PO-1037 | Invoice 37 | 230754000 | Posted
ACT-0038 | 2026-05-19 | 1.2 | CC-12 | V001 | PT Alpha Fabrication | PO-1038 | Invoice 38 | 231480000 | Posted
ACT-0039 | 2026-05-28 | 2.1 | CC-21 | V006 | PT Survey Indo | PO-1039 | Invoice 39 | 965983000 | Posted
ACT-0040 | 2026-05-27 | 2.2 | CC-22 | V005 | PT Mekanika Utama | PO-1040 | Invoice 40 | 500548000 | Posted
ACT-0041 | 2026-05-31 | 3.1 | CC-31 | V005 | PT Mekanika Utama | PO-1041 | Invoice 41 | 748449000 | Posted
ACT-0042 | 2026-05-15 | 3.2 | CC-32 | V003 | PT Kaltim Electrical | PO-1042 | Invoice 42 | 1107647000 | Posted
ACT-0043 | 2026-06-01 | 3.3 | CC-33 | V006 | PT Survey Indo | PO-1043 | Invoice 43 | 744670000 | Posted
ACT-0044 | 2026-05-25 | 4.0 | CC-40 | V003 | PT Kaltim Electrical | PO-1044 | Invoice 44 | 273933000 | Posted
ACT-0045 | 2026-05-20 | 5.0 | CC-50 | V001 | PT Alpha Fabrication | PO-1045 | Invoice 45 | 311600000 | Posted
ACT-0046 | 2026-06-22 | 1.1 | CC-11 | V004 | PT Prima Logistics | PO-1046 | Invoice 46 | 146374000 | Posted
ACT-0047 | 2026-06-30 | 1.2 | CC-12 | V005 | PT Mekanika Utama | PO-1047 | Invoice 47 | 218262000 | Posted
ACT-0048 | 2026-06-23 | 2.1 | CC-21 | V001 | PT Alpha Fabrication | PO-1048 | Invoice 48 | 1629151000 | Posted
ACT-0049 | 2026-06-20 | 2.2 | CC-22 | V006 | PT Survey Indo | PO-1049 | Invoice 49 | 737420000 | Posted
ACT-0050 | 2026-06-19 | 3.1 | CC-31 | V002 | PT Borneo Civil | PO-1050 | Invoice 50 | 499566000 | Posted
ACT-0051 | 2026-06-30 | 3.2 | CC-32 | V005 | PT Mekanika Utama | PO-1051 | Invoice 51 | 1097100000 | Posted
ACT-0052 | 2026-06-29 | 3.3 | CC-33 | V001 | PT Alpha Fabrication | PO-1052 | Invoice 52 | 687841000 | Posted
ACT-0053 | 2026-06-25 | 4.0 | CC-40 | V001 | PT Alpha Fabrication | PO-1053 | Invoice 53 | 164478000 | Posted
ACT-0054 | 2026-06-21 | 5.0 | CC-50 | V003 | PT Kaltim Electrical | PO-1054 | Invoice 54 | 297187000 | Posted
ACT-0055 | 2026-07-16 | 1.1 | CC-11 | V005 | PT Mekanika Utama | PO-1055 | Invoice 55 | 303658000 | Posted
ACT-0056 | 2026-07-16 | 1.2 | CC-12 | V006 | PT Survey Indo | PO-1056 | Invoice 56 | 181465000 | Posted
ACT-0057 | 2026-07-18 | 2.1 | CC-21 | V005 | PT Mekanika Utama | PO-1057 | Invoice 57 | 1531445000 | Posted
ACT-0058 | 2026-07-31 | 2.2 | CC-22 | V006 | PT Survey Indo | PO-1058 | Invoice 58 | 720151000 | Posted
ACT-0059 | 2026-08-02 | 3.1 | CC-31 | V002 | PT Borneo Civil | PO-1059 | Invoice 59 | 456023000 | Posted
ACT-0060 | 2026-07-31 | 3.2 | CC-32 | V004 | PT Prima Logistics | PO-1060 | Invoice 60 | 1103618000 | Posted
ACT-0061 | 2026-07-23 | 3.3 | CC-33 | V006 | PT Survey Indo | PO-1061 | Invoice 61 | 730272000 | Posted
ACT-0062 | 2026-08-03 | 4.0 | CC-40 | V004 | PT Prima Logistics | PO-1062 | Invoice 62 | 311692000 | Posted
ACT-0063 | 2026-07-30 | 5.0 | CC-50 | V003 | PT Kaltim Electrical | PO-1063 | Invoice 63 | 350160000 | Posted
ACT-9001 | 2026-07-18 | 3.2 | CC-32 | V005 | PT Mekanika Utama | PO-7788 | Mechanical erection invoice | 1250000000 | Posted
ACT-9002 | 2026-07-18 | 3.2 | CC-32 | V005 | PT Mekanika Utama | PO-7788 | Mechanical erection invoice | 1250000000 | Posted
ACT-9003 | 2026-07-21 |  | CC-31 | V002 | PT Borneo Civil | PO-7790 | Site grading | 420000000 | Posted
ACT-9004 | 2026-07-22 | 9.9 | CC-99 | V004 | PT Prima Logistics | PO-7791 | Unmapped logistics | 310000000 | Posted
ACT-9005 | 2026-07-24 | 2.2 | CC-22 | V004 | PT Prima Logistik | PO-7792 | Freight bulk material | 560000000 | Posted
ACT-9006 | 2026-08-02 | 3.1 | CC-31 | V002 | PT Borneo Civil | PO-7793 | Accelerated concrete package | 4600000000 | Posted
ACT-9007 | 2026-08-05 | 3.3 | CC-33 | V003 | PT Kaltim Electrical | PO-7794 | Cable procurement acceleration | 3800000000 | Posted
ACT-9008 | 2026-08-06 | 3.2 | CC-32 | V005 | PT Mekanika Utama | PO-7795 | Mechanical package A | 2900000000 | Posted
ACT-9009 | 2026-08-07 | 3.2 | CC-32 | V005 | PT Mekanika Utama | PO-7796 | Mechanical package B | 2600000000 | Posted
ACT-9010 | 2026-08-08 | 3.2 | CC-32 | V005 | PT Mekanika Utama | PO-7797 | Mechanical package C | 2300000000 | Posted

## Commitments
COMMITMENTS
commitment_id | wbs_code | po_number | vendor_id | vendor_name | committed_amount | invoiced_amount | status | commitment_date
COM-001 | 2.1 | PO-6001 | V001 | PT Alpha Fabrication | 18500000000 | 17000000000 | Open | 2026-03-01
COM-002 | 2.2 | PO-6002 | V004 | PT Prima Logistics | 8500000000 | 6700000000 | Open | 2026-03-10
COM-003 | 3.1 | PO-6003 | V002 | PT Borneo Civil | 7000000000 | 4900000000 | Open | 2026-04-01
COM-004 | 3.2 | PO-6004 | V005 | PT Mekanika Utama | 14000000000 | 7800000000 | Open | 2026-04-05
COM-005 | 3.3 | PO-6005 | V003 | PT Kaltim Electrical | 10500000000 | 6900000000 | Open | 2026-04-15
COM-006 | 4.0 | PO-6006 | V006 | PT Survey Indo | 3800000000 | 600000000 | Open | 2026-06-01

## Schedule
SCHEDULE
activity_id | wbs_code | activity_name | discipline | baseline_start | baseline_finish | actual_start | actual_finish | planned_progress | actual_progress | total_float_days | critical | status
A1000 | 1.1 | Process Design | Engineering | 2026-01-05 | 2026-03-15 | 2026-01-06 | 2026-03-30 | 100% | 100% | 0 | FALSE | Complete
A1010 | 1.2 | Civil Design | Engineering | 2026-01-10 | 2026-03-30 | 2026-01-12 | 2026-04-20 | 100% | 100% | 0 | FALSE | Complete
A2000 | 2.1 | Compressor Procurement | Procurement | 2026-02-01 | 2026-07-15 | 2026-02-03 |  | 100% | 82% | -12 | TRUE | In Progress
A2010 | 2.2 | Bulk Material Procurement | Procurement | 2026-02-15 | 2026-06-30 | 2026-02-20 |  | 100% | 88% | 4 | FALSE | In Progress
A3000 | 3.1 | Site Preparation | Construction | 2026-03-01 | 2026-05-15 | 2026-03-03 | 2026-05-28 | 100% | 100% | 0 | FALSE | Complete
A3010 | 3.1 | Foundation Works | Construction | 2026-04-01 | 2026-07-01 | 2026-04-05 |  | 100% | 68% | -8 | TRUE | In Progress
A3020 | 3.2 | Equipment Erection | Construction | 2026-06-01 | 2026-08-01 | 2026-06-10 |  | 95% | 55% | -18 | TRUE | In Progress
A3030 | 3.2 | Piping Installation | Construction | 2026-06-15 | 2026-09-15 | 2026-06-22 |  | 70% | 34% | -10 | TRUE | In Progress
A3040 | 3.3 | Cable Tray Installation | Construction | 2026-06-20 | 2026-08-10 | 2026-06-28 |  | 90% | 42% | -15 | TRUE | In Progress
A3050 | 3.3 | Cable Pulling | Construction | 2026-07-15 | 2026-09-05 | 2026-07-20 |  | 50% | 12% | 2 | FALSE | In Progress
A4000 | 4.0 | Pre-Commissioning | Commissioning | 2026-09-15 | 2026-11-01 |  |  | 0% | 0% | 6 | FALSE | Not Started
A4010 | 4.0 | Commissioning | Commissioning | 2026-11-02 | 2026-12-10 |  |  | 0% | 0% | 3 | TRUE | Not Started
A9990 | 5.0 | Temporary Facilities | Indirect | 2026-05-01 | 2026-06-15 | 2026-06-20 | 2026-06-10 | 100% | 115% | 5 | FALSE | Complete

## Progress
PROGRESS
progress_id | period | wbs_code | planned_progress | actual_progress | variance | status
PRG-11-1 | 2026-05-31 | 1.1 | 100% | 100% | 0% | Approved
PRG-11-2 | 2026-06-30 | 1.1 | 100% | 100% | 0% | Approved
PRG-11-3 | 2026-07-31 | 1.1 | 100% | 100% | 0% | Approved
PRG-11-4 | 2026-08-15 | 1.1 | 100% | 100% | 0% | Approved
PRG-12-1 | 2026-05-31 | 1.2 | 100% | 95% | -5% | Approved
PRG-12-2 | 2026-06-30 | 1.2 | 100% | 100% | 0% | Approved
PRG-12-3 | 2026-07-31 | 1.2 | 100% | 100% | 0% | Approved
PRG-12-4 | 2026-08-15 | 1.2 | 100% | 100% | 0% | Approved
PRG-21-1 | 2026-05-31 | 2.1 | 65% | 50% | -15% | Approved
PRG-21-2 | 2026-06-30 | 2.1 | 80% | 62% | -18% | Approved
PRG-21-3 | 2026-07-31 | 2.1 | 95% | 74% | -21% | Approved
PRG-21-4 | 2026-08-15 | 2.1 | 100% | 82% | -18% | Approved
PRG-22-1 | 2026-05-31 | 2.2 | 70% | 55% | -15% | Approved
PRG-22-2 | 2026-06-30 | 2.2 | 86% | 68% | -18% | Approved
PRG-22-3 | 2026-07-31 | 2.2 | 100% | 80% | -20% | Approved
PRG-22-4 | 2026-08-15 | 2.2 | 100% | 88% | -12% | Approved
PRG-31-1 | 2026-05-31 | 3.1 | 45% | 30% | -15% | Approved
PRG-31-2 | 2026-06-30 | 3.1 | 70% | 48% | -22% | Approved
PRG-31-3 | 2026-07-31 | 3.1 | 92% | 58% | -34% | Approved
PRG-31-4 | 2026-08-15 | 3.1 | 100% | 61% | -39% | Approved
PRG-32-1 | 2026-05-31 | 3.2 | 18% | 10% | -8% | Approved
PRG-32-2 | 2026-06-30 | 3.2 | 38% | 20% | -18% | Approved
PRG-32-3 | 2026-07-31 | 3.2 | 66% | 30% | -36% | Approved
PRG-32-4 | 2026-08-15 | 3.2 | 82% | 32% | -50% | Approved
PRG-33-1 | 2026-05-31 | 3.3 | 10% | 5% | -5% | Approved
PRG-33-2 | 2026-06-30 | 3.3 | 28% | 14% | -14% | Approved
PRG-33-3 | 2026-07-31 | 3.3 | 52% | 25% | -27% | Approved
PRG-33-4 | 2026-08-15 | 3.3 | 70% | 27% | -43% | Approved
PRG-40-1 | 2026-05-31 | 4.0 | 0% | 0% | 0% | Approved
PRG-40-2 | 2026-06-30 | 4.0 | 0% | 0% | 0% | Approved
PRG-40-3 | 2026-07-31 | 4.0 | 0% | 0% | 0% | Approved
PRG-40-4 | 2026-08-15 | 4.0 | 0% | 0% | 0% | Approved
PRG-50-1 | 2026-05-31 | 5.0 | 70% | 62% | -8% | Approved
PRG-50-2 | 2026-06-30 | 5.0 | 78% | 70% | -8% | Approved
PRG-50-3 | 2026-07-31 | 5.0 | 84% | 76% | -8% | Approved
PRG-50-4 | 2026-08-15 | 5.0 | 88% | 108% | 20% | Approved

## Expected_Findings
EXPECTED FINDINGS
expected_id | rule_id | category | severity | source | entity | finding_title | why_expected
EXP-001 | DQ-001 | Data Quality | Critical | Actual_Cost | ACT-9003 | Missing WBS Reference | Transaction has no WBS code.
EXP-002 | DQ-002 | Data Quality | Warning | Actual_Cost | ACT-9001/ACT-9002 | Duplicate Cost Transaction | Same date/WBS/vendor/PO/description/amount.
EXP-003 | DQ-003 | Data Quality | Critical | Schedule | A9990 | Contradictory Date / Progress | Actual finish precedes actual start and progress exceeds 100%.
EXP-004 | DQ-004 | Data Quality | Critical | Actual_Cost | ACT-9004 | Orphan WBS Reference | WBS 9.9 is not in WBS master.
EXP-005 | DQ-005 | Data Quality | Warning | Actual_Cost | ACT-9005 | Vendor Identity Inconsistency | Vendor ID V004 has inconsistent spelling.
EXP-006 | CST-001 | Cost | Critical | Actual_Cost | 3.1 | Actual Cost Exceeds Budget | Cumulative actual should exceed WBS budget after planted outlier.
EXP-007 | CST-001 | Cost | Critical | Actual_Cost | 3.2 | Actual Cost Exceeds Budget | Cumulative actual should exceed WBS budget.
EXP-008 | CST-002 | Cost | Critical | Actual_Cost+Commitments | 3.2 | Actual + Commitment Exceeds Budget | Actual plus open commitment exceeds WBS budget.
EXP-009 | CST-002 | Cost | Warning | Actual_Cost+Commitments | 3.3 | Actual + Commitment Exceeds Budget | Actual plus open commitment approaches/exceeds budget.
EXP-010 | CST-003 | Cost | Warning | Actual_Cost | 3.3 | Cost Spike vs Recent Run Rate | August cost materially exceeds recent run-rate.
EXP-011 | CST-004 | Cost | Warning | Actual_Cost | V005 | Vendor Concentration Risk | Large recent share of WBS 3.2 spend goes to V005.
EXP-012 | CST-005 | Cost | Critical | Actual_Cost | ACT-9006 | High-Value Transaction Outlier | Transaction materially exceeds peer transactions.
EXP-013 | CST-006 | Cross-domain | Critical | Actual_Cost+Progress | 3.2 | High Cost with Low Progress | High cost consumption while actual progress remains low.
EXP-014 | SCH-001 | Schedule | Critical | Schedule | A2000 | Overdue Activity | Baseline finish passed and activity incomplete.
EXP-015 | SCH-001 | Schedule | Critical | Schedule | A3020 | Overdue Activity | Baseline finish passed and activity incomplete.
EXP-016 | SCH-002 | Schedule | Warning | Schedule | A1000 | Baseline Finish Slippage | Actual finish is after baseline finish.
EXP-017 | SCH-002 | Schedule | Warning | Schedule | A1010 | Baseline Finish Slippage | Actual finish is after baseline finish.
EXP-018 | SCH-003 | Schedule | Critical | Schedule | A3020 | Critical Activity Delay | Critical activity is late.
EXP-019 | SCH-004 | Schedule | Warning | Schedule | A3040 | Activity Progress Lag | Actual progress is far below planned progress.
EXP-020 | SCH-005 | Schedule | Critical | Schedule | A3020 | Negative Total Float | Total float is negative.
EXP-021 | PRG-001 | Progress | Warning | Progress | 3.2 | WBS Progress Lag | Actual progress is far below planned.
EXP-022 | PRG-002 | Progress | Critical | Progress | 5.0 | Progress Above 100 Percent | Actual progress is 108%.
EXP-023 | PRG-003 | Cross-domain | Critical | Actual_Cost+Progress | 3.1 | Cost Rising While Progress Flat | Recent cost acceleration with limited progress gain.
EXP-024 | XDOM-001 | Cross-domain | Critical | Schedule+Actual_Cost | 3.2 | Schedule Delay with High Cost Exposure | Delayed critical workstream also has high cost exposure.

## Rule_Test_Matrix
RULE TEST MATRIX
rule_id | rule_name | inputs | test_logic | expected_findings
DQ-001 | Missing WBS Reference | Actual_Cost.wbs_code | blank/null WBS | EXP-001
DQ-002 | Duplicate Cost Transaction | Actual_Cost | duplicate composite transaction | EXP-002
DQ-003 | Contradictory Date / Progress | Schedule | actual_finish < actual_start OR progress > 100% | EXP-003
DQ-004 | Orphan WBS Reference | Actual_Cost + WBS | WBS not found in master | EXP-004
DQ-005 | Vendor Identity Inconsistency | Actual_Cost | same vendor ID, inconsistent normalized name | EXP-005
CST-001 | Actual Cost Exceeds Budget | Actual_Cost + Budget | SUM(actual) > budget by WBS | EXP-006/007
CST-002 | Actual + Commitment Exceeds Budget | Actual + Commitments + Budget | actual + open commitment > budget | EXP-008/009
CST-003 | Cost Spike vs Recent Run Rate | Actual_Cost | current spend > configured recent run-rate threshold | EXP-010
CST-004 | Vendor Concentration Risk | Actual_Cost | vendor share > threshold | EXP-011
CST-005 | High-Value Transaction Outlier | Actual_Cost | extreme transaction vs peers | EXP-012
CST-006 | High Cost with Low Progress | Actual_Cost + Progress | high cost consumption + low progress | EXP-013
SCH-001 | Overdue Activity | Schedule | baseline_finish < data_date AND incomplete | EXP-014/015
SCH-002 | Baseline Finish Slippage | Schedule | actual_finish > baseline_finish | EXP-016/017
SCH-003 | Critical Activity Delay | Schedule | critical AND late/incomplete | EXP-018
SCH-004 | Activity Progress Lag | Schedule | planned - actual > threshold | EXP-019
SCH-005 | Negative Total Float | Schedule | total_float_days < 0 | EXP-020
PRG-001 | WBS Progress Lag | Progress | planned - actual > threshold | EXP-021
PRG-002 | Progress Above 100 Percent | Progress | actual_progress > 1.0 | EXP-022
PRG-003 | Cost Rising While Progress Flat | Actual + Progress | spend increases while progress delta small | EXP-023
XDOM-001 | Schedule Delay with High Cost Exposure | Schedule + Actual | late critical workstream + material cost exposure | EXP-024

## README
CONTROL CHECK AI — SYNTHETIC PROJECT DATASET v0.1
Purpose | Ground-truth dataset for validating ingestion, data quality, cost, schedule, progress and cross-domain rules.
Project | EPC Gas Compression Facility Expansion
Data date | 2026-08-15
Currency | IDR
Ground-truth findings | 24
MVP rules covered | 20
Primary test | Engine should detect intentionally planted issues and retain evidence references.
Important | Synthetic data only. All names are fictional for testing.
Recommended run order | Ingest → map schema → validate → run rules → compare to Expected_Findings.
Evidence principle | Every finding should retain source dataset plus entity/row references.
Next artifact | Python rule-engine test harness and FastAPI control-check service.