## README
ControlCheck AI — Realistic EPC Dummy Dataset
Purpose | Production-like fictional EPC project data for ControlCheck ingestion and rule-engine testing
Project | Onshore Gas Compression Facility Expansion
Project ID | CC-DEMO-EPC-001
Data date | 2026-08-31
Currency | USD
Scale | USD 34.3 million approved control budget; 23 WBS nodes; 25 schedule activities
Important | All organizations, people, transactions, and values are fictional. Do not use for accounting.
How to use | Upload this workbook to ControlCheck AI. Canonical sheet names and row-3 headers are preserved.
Seeded risk themes
• | Cost overrun and commitment exposure
• | Cost spike and high-value milestone
• | Vendor concentration
• | Overdue and critical schedule activities
• | Negative float and progress lag
• | Duplicate and invalid WBS references
• | Vendor identity inconsistency
• | Progress above 100 percent

## Project_Info
project_field | value
project_id | CC-DEMO-EPC-001
project_name | Onshore Gas Compression Facility Expansion
data_date | 2026-08-31
dataset_version | 0.2
currency | USD

## WBS
WBS MASTER — ONSHORE GAS COMPRESSION EXPANSION
wbs_code | wbs_name | parent_wbs | discipline | level
1.0 | Engineering |  | Engineering | 1
1.1 | Process & Mechanical Engineering | 1.0 | Engineering | 2
1.2 | Civil & Structural Engineering | 1.0 | Engineering | 2
1.3 | Electrical & Instrument Engineering | 1.0 | Engineering | 2
1.4 | Construction Engineering & Workpacks | 1.0 | Engineering | 2
2.0 | Procurement |  | Procurement | 1
2.1 | Compressor Package | 2.0 | Procurement | 2
2.2 | Pressure Vessels & Skids | 2.0 | Procurement | 2
2.3 | Piping Bulk Materials | 2.0 | Procurement | 2
2.4 | Electrical & Instrument Materials | 2.0 | Procurement | 2
3.0 | Construction |  | Construction | 1
3.1 | Site Preparation & Civil Works | 3.0 | Construction | 2
3.2 | Equipment Foundations | 3.0 | Construction | 2
3.3 | Mechanical Equipment Erection | 3.0 | Construction | 2
3.4 | Piping Fabrication & Installation | 3.0 | Construction | 2
3.5 | Electrical & Instrument Installation | 3.0 | Construction | 2
4.0 | Pre-commissioning & Commissioning |  | Commissioning | 1
4.1 | Pre-commissioning | 4.0 | Commissioning | 2
4.2 | Commissioning & Performance Test | 4.0 | Commissioning | 2
5.0 | Project Management |  | Project Management | 1
5.1 | Project Management & Administration | 5.0 | Project Management | 2
5.2 | Project Controls | 5.0 | Project Controls | 2
5.3 | HSE, Quality & Site Services | 5.0 | HSE/Quality | 2

## Budget
APPROVED CONTROL BUDGET — USD
budget_id | wbs_code | cost_code | description | budget_amount | status | effective_date
BDG-11-MAT | 1.1 | MAT | Process & Mechanical Engineering — Equipment and material supply | 660000 | Approved | 2026-01-01
BDG-11-LAB | 1.1 | LAB | Process & Mechanical Engineering — Direct and indirect labor | 360000 | Approved | 2026-01-01
BDG-11-SUB | 1.1 | SUB | Process & Mechanical Engineering — Subcontract and specialist services | 180000 | Approved | 2026-01-01
BDG-12-MAT | 1.2 | MAT | Civil & Structural Engineering — Equipment and material supply | 495000 | Approved | 2026-01-01
BDG-12-LAB | 1.2 | LAB | Civil & Structural Engineering — Direct and indirect labor | 270000 | Approved | 2026-01-01
BDG-12-SUB | 1.2 | SUB | Civil & Structural Engineering — Subcontract and specialist services | 135000 | Approved | 2026-01-01
BDG-13-MAT | 1.3 | MAT | Electrical & Instrument Engineering — Equipment and material supply | 605000 | Approved | 2026-01-01
BDG-13-LAB | 1.3 | LAB | Electrical & Instrument Engineering — Direct and indirect labor | 330000 | Approved | 2026-01-01
BDG-13-SUB | 1.3 | SUB | Electrical & Instrument Engineering — Subcontract and specialist services | 165000 | Approved | 2026-01-01
BDG-14-MAT | 1.4 | MAT | Construction Engineering & Workpacks — Equipment and material supply | 550000 | Approved | 2026-01-01
BDG-14-LAB | 1.4 | LAB | Construction Engineering & Workpacks — Direct and indirect labor | 300000 | Approved | 2026-01-01
BDG-14-SUB | 1.4 | SUB | Construction Engineering & Workpacks — Subcontract and specialist services | 150000 | Approved | 2026-01-01
BDG-21-MAT | 2.1 | MAT | Compressor Package — Equipment and material supply | 4180000 | Approved | 2026-01-01
BDG-21-LAB | 2.1 | LAB | Compressor Package — Direct and indirect labor | 2280000 | Approved | 2026-01-01
BDG-21-SUB | 2.1 | SUB | Compressor Package — Subcontract and specialist services | 1140000 | Approved | 2026-01-01
BDG-22-MAT | 2.2 | MAT | Pressure Vessels & Skids — Equipment and material supply | 1430000 | Approved | 2026-01-01
BDG-22-LAB | 2.2 | LAB | Pressure Vessels & Skids — Direct and indirect labor | 780000 | Approved | 2026-01-01
BDG-22-SUB | 2.2 | SUB | Pressure Vessels & Skids — Subcontract and specialist services | 390000 | Approved | 2026-01-01
BDG-23-MAT | 2.3 | MAT | Piping Bulk Materials — Equipment and material supply | 1760000 | Approved | 2026-01-01
BDG-23-LAB | 2.3 | LAB | Piping Bulk Materials — Direct and indirect labor | 960000 | Approved | 2026-01-01
BDG-23-SUB | 2.3 | SUB | Piping Bulk Materials — Subcontract and specialist services | 480000 | Approved | 2026-01-01
BDG-24-MAT | 2.4 | MAT | Electrical & Instrument Materials — Equipment and material supply | 1155000 | Approved | 2026-01-01
BDG-24-LAB | 2.4 | LAB | Electrical & Instrument Materials — Direct and indirect labor | 630000 | Approved | 2026-01-01
BDG-24-SUB | 2.4 | SUB | Electrical & Instrument Materials — Subcontract and specialist services | 315000 | Approved | 2026-01-01
BDG-31-MAT | 3.1 | MAT | Site Preparation & Civil Works — Equipment and material supply | 1100000 | Approved | 2026-01-01
BDG-31-LAB | 3.1 | LAB | Site Preparation & Civil Works — Direct and indirect labor | 600000 | Approved | 2026-01-01
BDG-31-SUB | 3.1 | SUB | Site Preparation & Civil Works — Subcontract and specialist services | 300000 | Approved | 2026-01-01
BDG-32-MAT | 3.2 | MAT | Equipment Foundations — Equipment and material supply | 1265000 | Approved | 2026-01-01
BDG-32-LAB | 3.2 | LAB | Equipment Foundations — Direct and indirect labor | 690000 | Approved | 2026-01-01
BDG-32-SUB | 3.2 | SUB | Equipment Foundations — Subcontract and specialist services | 345000 | Approved | 2026-01-01
BDG-33-MAT | 3.3 | MAT | Mechanical Equipment Erection — Equipment and material supply | 1210000 | Approved | 2026-01-01
BDG-33-LAB | 3.3 | LAB | Mechanical Equipment Erection — Direct and indirect labor | 660000 | Approved | 2026-01-01
BDG-33-SUB | 3.3 | SUB | Mechanical Equipment Erection — Subcontract and specialist services | 330000 | Approved | 2026-01-01
BDG-34-MAT | 3.4 | MAT | Piping Fabrication & Installation — Equipment and material supply | 1100000 | Approved | 2026-01-01
BDG-34-LAB | 3.4 | LAB | Piping Fabrication & Installation — Direct and indirect labor | 600000 | Approved | 2026-01-01
BDG-34-SUB | 3.4 | SUB | Piping Fabrication & Installation — Subcontract and specialist services | 300000 | Approved | 2026-01-01
BDG-35-MAT | 3.5 | MAT | Electrical & Instrument Installation — Equipment and material supply | 825000 | Approved | 2026-01-01
BDG-35-LAB | 3.5 | LAB | Electrical & Instrument Installation — Direct and indirect labor | 450000 | Approved | 2026-01-01
BDG-35-SUB | 3.5 | SUB | Electrical & Instrument Installation — Subcontract and specialist services | 225000 | Approved | 2026-01-01
BDG-41-MAT | 4.1 | MAT | Pre-commissioning — Equipment and material supply | 440000 | Approved | 2026-01-01
BDG-41-LAB | 4.1 | LAB | Pre-commissioning — Direct and indirect labor | 240000 | Approved | 2026-01-01
BDG-41-SUB | 4.1 | SUB | Pre-commissioning — Subcontract and specialist services | 120000 | Approved | 2026-01-01
BDG-42-MAT | 4.2 | MAT | Commissioning & Performance Test — Equipment and material supply | 385000 | Approved | 2026-01-01
BDG-42-LAB | 4.2 | LAB | Commissioning & Performance Test — Direct and indirect labor | 210000 | Approved | 2026-01-01
BDG-42-SUB | 4.2 | SUB | Commissioning & Performance Test — Subcontract and specialist services | 105000 | Approved | 2026-01-01
BDG-51-MAT | 5.1 | MAT | Project Management & Administration — Equipment and material supply | 605000 | Approved | 2026-01-01
BDG-51-LAB | 5.1 | LAB | Project Management & Administration — Direct and indirect labor | 330000 | Approved | 2026-01-01
BDG-51-SUB | 5.1 | SUB | Project Management & Administration — Subcontract and specialist services | 165000 | Approved | 2026-01-01
BDG-52-MAT | 5.2 | MAT | Project Controls — Equipment and material supply | 275000 | Approved | 2026-01-01
BDG-52-LAB | 5.2 | LAB | Project Controls — Direct and indirect labor | 150000 | Approved | 2026-01-01
BDG-52-SUB | 5.2 | SUB | Project Controls — Subcontract and specialist services | 75000 | Approved | 2026-01-01
BDG-53-MAT | 5.3 | MAT | HSE, Quality & Site Services — Equipment and material supply | 385000 | Approved | 2026-01-01
BDG-53-LAB | 5.3 | LAB | HSE, Quality & Site Services — Direct and indirect labor | 210000 | Approved | 2026-01-01
BDG-53-SUB | 5.3 | SUB | HSE, Quality & Site Services — Subcontract and specialist services | 105000 | Approved | 2026-01-01

## Actual_Cost
ACTUAL COST LEDGER — POSTED THROUGH 2026-08-31
transaction_id | transaction_date | wbs_code | cost_code | vendor_id | vendor_name | po_number | description | actual_amount | status
TX-11-01-1 | 2026-01-28 | 1.1 | MAT | VEN-ENG-001 | Vector Engineering Services | PO-11-1 | Process & Mechanical Engineering — primary progress invoice | 141120 | Posted
TX-11-02-2 | 2026-02-25 | 1.1 | LAB | VEN-ENG-002 | Archipelago Design Partners | PO-11-2 | Process & Mechanical Engineering — support services | 211680 | Posted
TX-11-03-3 | 2026-03-27 | 1.1 | SUB | VEN-ENG-003 | Delta Technical Consultants | PO-11-3 | Process & Mechanical Engineering — specialist subcontract | 235200 | Posted
TX-11-04-1 | 2026-04-27 | 1.1 | MAT | VEN-ENG-001 | Vector Engineering Services | PO-11-1 | Process & Mechanical Engineering — primary progress invoice | 211680 | Posted
TX-11-05-2 | 2026-05-27 | 1.1 | LAB | VEN-ENG-002 | Archipelago Design Partners | PO-11-2 | Process & Mechanical Engineering — support services | 152880 | Posted
TX-11-06-3 | 2026-06-26 | 1.1 | SUB | VEN-ENG-003 | Delta Technical Consultants | PO-11-3 | Process & Mechanical Engineering — specialist subcontract | 105840 | Posted
TX-11-07-2 | 2026-07-28 | 1.1 | LAB | VEN-ENG-002 | Archipelago Design Partners | PO-11-2 | Process & Mechanical Engineering — support services | 70560 | Posted
TX-11-08-1 | 2026-08-27 | 1.1 | MAT | VEN-ENG-001 | Vector Engineering Services | PO-11-1 | Process & Mechanical Engineering — primary progress invoice | 47040 | Posted
TX-12-01-1 | 2026-01-28 | 1.2 | MAT | VEN-ENG-001 | Vector Engineering Services | PO-12-1 | Civil & Structural Engineering — primary progress invoice | 110160 | Posted
TX-12-02-2 | 2026-02-25 | 1.2 | LAB | VEN-ENG-002 | Archipelago Design Partners | PO-12-2 | Civil & Structural Engineering — support services | 165240 | Posted
TX-12-03-3 | 2026-03-27 | 1.2 | SUB | VEN-ENG-003 | Delta Technical Consultants | PO-12-3 | Civil & Structural Engineering — specialist subcontract | 183600 | Posted
TX-12-04-1 | 2026-04-27 | 1.2 | MAT | VEN-ENG-001 | Vector Engineering Services | PO-12-1 | Civil & Structural Engineering — primary progress invoice | 165240 | Posted
TX-12-05-2 | 2026-05-27 | 1.2 | LAB | VEN-ENG-002 | Archipelago Design Partners | PO-12-2 | Civil & Structural Engineering — support services | 119340 | Posted
TX-12-06-3 | 2026-06-26 | 1.2 | SUB | VEN-ENG-003 | Delta Technical Consultants | PO-12-3 | Civil & Structural Engineering — specialist subcontract | 82620 | Posted
TX-12-07-2 | 2026-07-28 | 1.2 | LAB | VEN-ENG-002 | Archipelago Design Partners | PO-12-2 | Civil & Structural Engineering — support services | 55080 | Posted
TX-12-08-1 | 2026-08-27 | 1.2 | MAT | VEN-ENG-001 | Vector Engineering Services | PO-12-1 | Civil & Structural Engineering — primary progress invoice | 36720 | Posted
TX-13-01-1 | 2026-01-28 | 1.3 | MAT | VEN-ENG-001 | Vector Engineering Services | PO-13-1 | Electrical & Instrument Engineering — primary progress invoice | 122760 | Posted
TX-13-02-2 | 2026-02-25 | 1.3 | LAB | VEN-ENG-002 | Archipelago Design Partners | PO-13-2 | Electrical & Instrument Engineering — support services | 184140 | Posted
TX-13-03-3 | 2026-03-27 | 1.3 | SUB | VEN-ENG-003 | Delta Technical Consultants | PO-13-3 | Electrical & Instrument Engineering — specialist subcontract | 204600 | Posted
TX-13-04-1 | 2026-04-27 | 1.3 | MAT | VEN-ENG-001 | Vector Engineering Services | PO-13-1 | Electrical & Instrument Engineering — primary progress invoice | 184140 | Posted
TX-13-05-2 | 2026-05-27 | 1.3 | LAB | VEN-ENG-002 | Archipelago Design Partners | PO-13-2 | Electrical & Instrument Engineering — support services | 132990 | Posted
TX-13-06-3 | 2026-06-26 | 1.3 | SUB | VEN-ENG-003 | Delta Technical Consultants | PO-13-3 | Electrical & Instrument Engineering — specialist subcontract | 92070 | Posted
TX-13-07-2 | 2026-07-28 | 1.3 | LAB | VEN-ENG-002 | Archipelago Design Partners | PO-13-2 | Electrical & Instrument Engineering — support services | 61380 | Posted
TX-13-08-1 | 2026-08-27 | 1.3 | MAT | VEN-ENG-001 | Vector Engineering Services | PO-13-1 | Electrical & Instrument Engineering — primary progress invoice | 40920 | Posted
TX-14-01-1 | 2026-01-28 | 1.4 | MAT | VEN-ENG-001 | Vector Engineering Services | PO-14-1 | Construction Engineering & Workpacks — primary progress invoice | 105600 | Posted
TX-14-02-2 | 2026-02-25 | 1.4 | LAB | VEN-ENG-002 | Archipelago Design Partners | PO-14-2 | Construction Engineering & Workpacks — support services | 158400 | Posted
TX-14-03-3 | 2026-03-27 | 1.4 | SUB | VEN-ENG-003 | Delta Technical Consultants | PO-14-3 | Construction Engineering & Workpacks — specialist subcontract | 176000 | Posted
TX-14-04-1 | 2026-04-27 | 1.4 | MAT | VEN-ENG-001 | Vector Engineering Services | PO-14-1 | Construction Engineering & Workpacks — primary progress invoice | 158400 | Posted
TX-14-05-2 | 2026-05-27 | 1.4 | LAB | VEN-ENG-002 | Archipelago Design Partners | PO-14-2 | Construction Engineering & Workpacks — support services | 114400 | Posted
TX-14-06-3 | 2026-06-26 | 1.4 | SUB | VEN-ENG-003 | Delta Technical Consultants | PO-14-3 | Construction Engineering & Workpacks — specialist subcontract | 79200 | Posted
TX-14-07-2 | 2026-07-28 | 1.4 | LAB | VEN-ENG-002 | Archipelago Design Partners | PO-14-2 | Construction Engineering & Workpacks — support services | 52800 | Posted
TX-14-08-1 | 2026-08-27 | 1.4 | MAT | VEN-ENG-001 | Vector Engineering Services | PO-14-1 | Construction Engineering & Workpacks — primary progress invoice | 35200 | Posted
TX-21-01-2 | 2026-01-28 | 2.1 | LAB | VEN-PRC-002 | Pacific Industrial Supply | PO-21-2 | Compressor Package — support services | 311600 | Posted
TX-21-02-1 | 2026-02-25 | 2.1 | MAT | VEN-PRC-001 | Atlas Rotating Equipment | PO-21-1 | Compressor Package — primary progress invoice | 498560 | Posted
TX-21-03-1 | 2026-03-27 | 2.1 | MAT | VEN-PRC-001 | Atlas Rotating Equipment | PO-21-1 | Compressor Package — primary progress invoice | 747840 | Posted
TX-21-04-1 | 2026-04-27 | 2.1 | MAT | VEN-PRC-001 | Atlas Rotating Equipment | PO-21-1 | Compressor Package — primary progress invoice | 1121760 | Posted
TX-21-05-1 | 2026-05-27 | 2.1 | MAT | VEN-PRC-001 | Atlas Rotating Equipment | PO-21-1 | Compressor Package — primary progress invoice | 1121760 | Posted
TX-21-06-1 | 2026-06-26 | 2.1 | MAT | VEN-PRC-001 | Atlas Rotating Equipment | PO-21-1 | Compressor Package — primary progress invoice | 934800 | Posted
TX-21-07-1 | 2026-07-28 | 2.1 | MAT | VEN-PRC-001 | Atlas Rotating Equipment | PO-21-1 | Compressor Package — primary progress invoice | 747840 | Posted
TX-21-08-1 | 2026-08-27 | 2.1 | MAT | VEN-PRC-001 | Atlas Rotating Equipment | PO-21-1 | Compressor Package — primary progress invoice | 747840 | Posted
TX-22-01-1 | 2026-01-28 | 2.2 | MAT | VEN-PRC-001 | Atlas Rotating Equipment | PO-22-1 | Pressure Vessels & Skids — primary progress invoice | 45500 | Posted
TX-22-02-2 | 2026-02-25 | 2.2 | LAB | VEN-PRC-002 | Pacific Industrial Supply | PO-22-2 | Pressure Vessels & Skids — support services | 72800 | Posted
TX-22-03-3 | 2026-03-27 | 2.2 | SUB | VEN-PRC-004 | Eastern Process Equipment | PO-22-3 | Pressure Vessels & Skids — specialist subcontract | 109200 | Posted
TX-22-04-1 | 2026-04-27 | 2.2 | MAT | VEN-PRC-001 | Atlas Rotating Equipment | PO-22-1 | Pressure Vessels & Skids — primary progress invoice | 163800 | Posted
TX-22-05-2 | 2026-05-27 | 2.2 | LAB | VEN-PRC-002 | Pacific Industrial Supply | PO-22-2 | Pressure Vessels & Skids — support services | 163800 | Posted
TX-22-06-3 | 2026-06-26 | 2.2 | SUB | VEN-PRC-004 | Eastern Process Equipment | PO-22-3 | Pressure Vessels & Skids — specialist subcontract | 136500 | Posted
TX-22-07-2 | 2026-07-28 | 2.2 | LAB | VEN-PRC-002 | Pacific Industrial Supply | PO-22-2 | Pressure Vessels & Skids — support services | 109200 | Posted
TX-22-08-1 | 2026-08-27 | 2.2 | MAT | VEN-PRC-001 | Atlas Rotating Equipment | PO-22-1 | Pressure Vessels & Skids — primary progress invoice | 109200 | Posted
TX-22-MILESTONE-01 | 2026-04-15 | 2.2 | MAT | VEN-PRC-003 | Nusantara Piping Solutions Ltd | PO-22-1 | Fabrication milestone payment — pressure vessel skids | 1040000 | Posted
TX-23-01-1 | 2026-01-28 | 2.3 | MAT | VEN-PRC-001 | Atlas Rotating Equipment | PO-23-1 | Piping Bulk Materials — primary progress invoice | 108800 | Posted
TX-23-02-2 | 2026-02-25 | 2.3 | LAB | VEN-PRC-002 | Pacific Industrial Supply | PO-23-2 | Piping Bulk Materials — support services | 174080 | Posted
TX-23-03-3 | 2026-03-27 | 2.3 | SUB | VEN-PRC-004 | Eastern Process Equipment | PO-23-3 | Piping Bulk Materials — specialist subcontract | 261120 | Posted
TX-23-04-1 | 2026-04-27 | 2.3 | MAT | VEN-PRC-001 | Atlas Rotating Equipment | PO-23-1 | Piping Bulk Materials — primary progress invoice | 391680 | Posted
TX-23-05-2 | 2026-05-27 | 2.3 | LAB | VEN-PRC-002 | Pacific Industrial Supply | PO-23-2 | Piping Bulk Materials — support services | 391680 | Posted
TX-23-06-3 | 2026-06-26 | 2.3 | SUB | VEN-PRC-004 | Eastern Process Equipment | PO-23-3 | Piping Bulk Materials — specialist subcontract | 326400 | Posted
TX-23-07-2 | 2026-07-28 | 2.3 | LAB | VEN-PRC-002 | Pacific Industrial Supply | PO-23-2 | Piping Bulk Materials — support services | 261120 | Posted
TX-23-08-1 | 2026-08-27 | 2.3 | MAT | VEN-PRC-001 | Atlas Rotating Equipment | PO-23-1 | Piping Bulk Materials — primary progress invoice | 261120 | Posted
TX-24-01-1 | 2026-01-28 | 2.4 | MAT | VEN-PRC-001 | Atlas Rotating Equipment | PO-24-1 | Electrical & Instrument Materials — primary progress invoice | 65100 | Posted
TX-24-02-2 | 2026-02-25 | 2.4 | LAB | VEN-PRC-002 | Pacific Industrial Supply | PO-24-2 | Electrical & Instrument Materials — support services | 104160 | Posted
TX-24-03-3 | 2026-03-27 | 2.4 | SUB | VEN-PRC-004 | Eastern Process Equipment | PO-24-3 | Electrical & Instrument Materials — specialist subcontract | 156240 | Posted
TX-24-04-1 | 2026-04-27 | 2.4 | MAT | VEN-PRC-001 | Atlas Rotating Equipment | PO-24-1 | Electrical & Instrument Materials — primary progress invoice | 234360 | Posted
TX-24-05-2 | 2026-05-27 | 2.4 | LAB | VEN-PRC-002 | Pacific Industrial Supply | PO-24-2 | Electrical & Instrument Materials — support services | 234360 | Posted
TX-24-06-3 | 2026-06-26 | 2.4 | SUB | VEN-PRC-004 | Eastern Process Equipment | PO-24-3 | Electrical & Instrument Materials — specialist subcontract | 195300 | Posted
TX-24-07-2 | 2026-07-28 | 2.4 | LAB | VEN-PRC-002 | Pacific Industrial Supply | PO-24-2 | Electrical & Instrument Materials — support services | 156240 | Posted
TX-24-08-1 | 2026-08-27 | 2.4 | MAT | VEN-PRC-001 | Atlas Rotating Equipment | PO-24-1 | Electrical & Instrument Materials — primary progress invoice | 156240 | Posted
TX-31-01-1 | 2026-01-28 | 3.1 | MAT | VEN-CON-001 | Borneo EPC Construction | PO-31-1 | Site Preparation & Civil Works — primary progress invoice | 92000 | Posted
TX-31-02-2 | 2026-02-25 | 3.1 | LAB | VEN-CON-002 | Nusantara Field Services | PO-31-2 | Site Preparation & Civil Works — support services | 128800 | Posted
TX-31-03-3 | 2026-03-27 | 3.1 | SUB | VEN-CON-003 | Sulawesi Industrial Contractors | PO-31-3 | Site Preparation & Civil Works — specialist subcontract | 184000 | Posted
TX-31-04-1 | 2026-04-27 | 3.1 | MAT | VEN-CON-001 | Borneo EPC Construction | PO-31-1 | Site Preparation & Civil Works — primary progress invoice | 239200 | Posted
TX-31-05-2 | 2026-05-27 | 3.1 | LAB | VEN-CON-002 | Nusantara Field Services | PO-31-2 | Site Preparation & Civil Works — support services | 276000 | Posted
TX-31-06-3 | 2026-06-26 | 3.1 | SUB | VEN-CON-003 | Sulawesi Industrial Contractors | PO-31-3 | Site Preparation & Civil Works — specialist subcontract | 294400 | Posted
TX-31-07-2 | 2026-07-28 | 3.1 | LAB | VEN-CON-002 | Nusantara Field Services | PO-31-2 | Site Preparation & Civil Works — support services | 294400 | Posted
TX-31-08-1 | 2026-08-27 | 3.1 | MAT | VEN-CON-001 | Borneo EPC Construction | PO-31-1 | Site Preparation & Civil Works — primary progress invoice | 331200 | Posted
TX-32-01-1 | 2026-01-28 | 3.2 | MAT | VEN-CON-001 | Borneo EPC Construction | PO-32-1 | Equipment Foundations — primary progress invoice | 124200 | Posted
TX-32-02-2 | 2026-02-25 | 3.2 | LAB | VEN-CON-002 | Nusantara Field Services | PO-32-2 | Equipment Foundations — support services | 173880 | Posted
TX-32-03-3 | 2026-03-27 | 3.2 | SUB | VEN-CON-003 | Sulawesi Industrial Contractors | PO-32-3 | Equipment Foundations — specialist subcontract | 248400 | Posted
TX-32-04-1 | 2026-04-27 | 3.2 | MAT | VEN-CON-001 | Borneo EPC Construction | PO-32-1 | Equipment Foundations — primary progress invoice | 322920 | Posted
TX-32-05-2 | 2026-05-27 | 3.2 | LAB | VEN-CON-002 | Nusantara Field Services | PO-32-2 | Equipment Foundations — support services | 372600 | Posted
TX-32-06-3 | 2026-06-26 | 3.2 | SUB | VEN-CON-003 | Sulawesi Industrial Contractors | PO-32-3 | Equipment Foundations — specialist subcontract | 397440 | Posted
TX-32-07-2 | 2026-07-28 | 3.2 | LAB | VEN-CON-002 | Nusantara Field Services | PO-32-2 | Equipment Foundations — support services | 397440 | Posted
TX-32-08-1 | 2026-08-27 | 3.2 | MAT | VEN-CON-001 | Borneo EPC Construction | PO-32-1 | Equipment Foundations — primary progress invoice | 447120 | Posted
TX-33-01-1 | 2026-01-28 | 3.3 | MAT | VEN-CON-001 | Borneo EPC Construction | PO-33-1 | Mechanical Equipment Erection — primary progress invoice | 47520 | Posted
TX-33-02-2 | 2026-02-25 | 3.3 | LAB | VEN-CON-002 | Nusantara Field Services | PO-33-2 | Mechanical Equipment Erection — support services | 63360 | Posted
TX-33-03-3 | 2026-03-27 | 3.3 | SUB | VEN-CON-003 | Sulawesi Industrial Contractors | PO-33-3 | Mechanical Equipment Erection — specialist subcontract | 95040 | Posted
TX-33-04-1 | 2026-04-27 | 3.3 | MAT | VEN-CON-001 | Borneo EPC Construction | PO-33-1 | Mechanical Equipment Erection — primary progress invoice | 126720 | Posted
TX-33-05-2 | 2026-05-27 | 3.3 | LAB | VEN-CON-002 | Nusantara Field Services | PO-33-2 | Mechanical Equipment Erection — support services | 158400 | Posted
TX-33-06-3 | 2026-06-26 | 3.3 | SUB | VEN-CON-003 | Sulawesi Industrial Contractors | PO-33-3 | Mechanical Equipment Erection — specialist subcontract | 190080 | Posted
TX-33-07-2 | 2026-07-28 | 3.3 | LAB | VEN-CON-002 | Nusantara Field Services | PO-33-2 | Mechanical Equipment Erection — support services | 205920 | Posted
TX-33-08-1 | 2026-08-27 | 3.3 | MAT | VEN-CON-001 | Borneo EPC Construction | PO-33-1 | Mechanical Equipment Erection — primary progress invoice | 696960 | Posted
TX-34-01-1 | 2026-01-28 | 3.4 | MAT | VEN-CON-001 | Borneo EPC Construction | PO-34-1 | Piping Fabrication & Installation — primary progress invoice | 55000 | Posted
TX-34-02-2 | 2026-02-25 | 3.4 | LAB | VEN-CON-002 | Nusantara Field Services | PO-34-2 | Piping Fabrication & Installation — support services | 77000 | Posted
TX-34-03-3 | 2026-03-27 | 3.4 | SUB | VEN-CON-003 | Sulawesi Industrial Contractors | PO-34-3 | Piping Fabrication & Installation — specialist subcontract | 110000 | Posted
TX-34-04-1 | 2026-04-27 | 3.4 | MAT | VEN-CON-001 | Borneo EPC Construction | PO-34-1 | Piping Fabrication & Installation — primary progress invoice | 143000 | Posted
TX-34-05-2 | 2026-05-27 | 3.4 | LAB | VEN-CON-002 | Nusantara Field Services | PO-34-2 | Piping Fabrication & Installation — support services | 165000 | Posted
TX-34-06-3 | 2026-06-26 | 3.4 | SUB | VEN-CON-003 | Sulawesi Industrial Contractors | PO-34-3 | Piping Fabrication & Installation — specialist subcontract | 176000 | Posted
TX-34-07-2 | 2026-07-28 | 3.4 | LAB | VEN-CON-002 | Nusantara Field Services | PO-34-2 | Piping Fabrication & Installation — support services | 176000 | Posted
TX-34-08-1 | 2026-08-27 | 3.4 | MAT | VEN-CON-001 | Borneo EPC Construction | PO-34-1 | Piping Fabrication & Installation — primary progress invoice | 198000 | Posted
TX-35-01-1 | 2026-01-28 | 3.5 | MAT | VEN-CON-001 | Borneo EPC Construction | PO-35-1 | Electrical & Instrument Installation — primary progress invoice | 36000 | Posted
TX-35-02-2 | 2026-02-25 | 3.5 | LAB | VEN-CON-002 | Nusantara Field Services | PO-35-2 | Electrical & Instrument Installation — support services | 50400 | Posted
TX-35-03-3 | 2026-03-27 | 3.5 | SUB | VEN-CON-003 | Sulawesi Industrial Contractors | PO-35-3 | Electrical & Instrument Installation — specialist subcontract | 72000 | Posted
TX-35-04-1 | 2026-04-27 | 3.5 | MAT | VEN-CON-001 | Borneo EPC Construction | PO-35-1 | Electrical & Instrument Installation — primary progress invoice | 93600 | Posted
TX-35-05-2 | 2026-05-27 | 3.5 | LAB | VEN-CON-002 | Nusantara Field Services | PO-35-2 | Electrical & Instrument Installation — support services | 108000 | Posted
TX-35-06-3 | 2026-06-26 | 3.5 | SUB | VEN-CON-003 | Sulawesi Industrial Contractors | PO-35-3 | Electrical & Instrument Installation — specialist subcontract | 115200 | Posted
TX-35-07-2 | 2026-07-28 | 3.5 | LAB | VEN-CON-002 | Nusantara Field Services | PO-35-2 | Electrical & Instrument Installation — support services | 115200 | Posted
TX-35-08-1 | 2026-08-27 | 3.5 | MAT | VEN-CON-001 | Borneo EPC Construction | PO-35-1 | Electrical & Instrument Installation — primary progress invoice | 129600 | Posted
TX-41-01-1 | 2026-01-28 | 4.1 | MAT | VEN-COM-001 | Commissioning Dynamics Asia | PO-41-1 | Pre-commissioning — primary progress invoice | 6000 | Posted
TX-41-02-2 | 2026-02-25 | 4.1 | LAB | VEN-COM-002 | Reliability Test Solutions | PO-41-2 | Pre-commissioning — support services | 8400 | Posted
TX-41-03-3 | 2026-03-27 | 4.1 | SUB | VEN-COM-003 | Process Start-up Partners | PO-41-3 | Pre-commissioning — specialist subcontract | 12000 | Posted
TX-41-04-1 | 2026-04-27 | 4.1 | MAT | VEN-COM-001 | Commissioning Dynamics Asia | PO-41-1 | Pre-commissioning — primary progress invoice | 15600 | Posted
TX-41-05-2 | 2026-05-27 | 4.1 | LAB | VEN-COM-002 | Reliability Test Solutions | PO-41-2 | Pre-commissioning — support services | 18000 | Posted
TX-41-06-3 | 2026-06-26 | 4.1 | SUB | VEN-COM-003 | Process Start-up Partners | PO-41-3 | Pre-commissioning — specialist subcontract | 19200 | Posted
TX-41-07-2 | 2026-07-28 | 4.1 | LAB | VEN-COM-002 | Reliability Test Solutions | PO-41-2 | Pre-commissioning — support services | 19200 | Posted
TX-41-08-1 | 2026-08-27 | 4.1 | MAT | VEN-COM-001 | Commissioning Dynamics Asia | PO-41-1 | Pre-commissioning — primary progress invoice | 21600 | Posted
TX-42-01-1 | 2026-01-28 | 4.2 | MAT | VEN-COM-001 | Commissioning Dynamics Asia | PO-42-1 | Commissioning & Performance Test — primary progress invoice | 1750 | Posted
TX-42-02-2 | 2026-02-25 | 4.2 | LAB | VEN-COM-002 | Reliability Test Solutions | PO-42-2 | Commissioning & Performance Test — support services | 2450 | Posted
TX-42-03-3 | 2026-03-27 | 4.2 | SUB | VEN-COM-003 | Process Start-up Partners | PO-42-3 | Commissioning & Performance Test — specialist subcontract | 3500 | Posted
TX-42-04-1 | 2026-04-27 | 4.2 | MAT | VEN-COM-001 | Commissioning Dynamics Asia | PO-42-1 | Commissioning & Performance Test — primary progress invoice | 4550 | Posted
TX-42-05-2 | 2026-05-27 | 4.2 | LAB | VEN-COM-002 | Reliability Test Solutions | PO-42-2 | Commissioning & Performance Test — support services | 5250 | Posted
TX-42-06-3 | 2026-06-26 | 4.2 | SUB | VEN-COM-003 | Process Start-up Partners | PO-42-3 | Commissioning & Performance Test — specialist subcontract | 5600 | Posted
TX-42-07-2 | 2026-07-28 | 4.2 | LAB | VEN-COM-002 | Reliability Test Solutions | PO-42-2 | Commissioning & Performance Test — support services | 5600 | Posted
TX-42-08-1 | 2026-08-27 | 4.2 | MAT | VEN-COM-001 | Commissioning Dynamics Asia | PO-42-1 | Commissioning & Performance Test — primary progress invoice | 6300 | Posted
TX-51-01-1 | 2026-01-28 | 5.1 | MAT | VEN-PMO-001 | ControlWorks Consulting | PO-51-1 | Project Management & Administration — primary progress invoice | 41250 | Posted
TX-51-02-2 | 2026-02-25 | 5.1 | LAB | VEN-PMO-002 | Integrated Site Support | PO-51-2 | Project Management & Administration — support services | 57750 | Posted
TX-51-03-3 | 2026-03-27 | 5.1 | SUB | VEN-PMO-003 | Project Assurance Group | PO-51-3 | Project Management & Administration — specialist subcontract | 82500 | Posted
TX-51-04-1 | 2026-04-27 | 5.1 | MAT | VEN-PMO-001 | ControlWorks Consulting | PO-51-1 | Project Management & Administration — primary progress invoice | 107250 | Posted
TX-51-05-2 | 2026-05-27 | 5.1 | LAB | VEN-PMO-002 | Integrated Site Support | PO-51-2 | Project Management & Administration — support services | 123750 | Posted
TX-51-06-3 | 2026-06-26 | 5.1 | SUB | VEN-PMO-003 | Project Assurance Group | PO-51-3 | Project Management & Administration — specialist subcontract | 132000 | Posted
TX-51-07-2 | 2026-07-28 | 5.1 | LAB | VEN-PMO-002 | Integrated Site Support | PO-51-2 | Project Management & Administration — support services | 132000 | Posted
TX-51-08-1 | 2026-08-27 | 5.1 | MAT | VEN-PMO-001 | ControlWorks Consulting | PO-51-1 | Project Management & Administration — primary progress invoice | 148500 | Posted
TX-52-01-1 | 2026-01-28 | 5.2 | MAT | VEN-PMO-001 | ControlWorks Consulting | PO-52-1 | Project Controls — primary progress invoice | 17500 | Posted
TX-52-02-2 | 2026-02-25 | 5.2 | LAB | VEN-PMO-002 | Integrated Site Support | PO-52-2 | Project Controls — support services | 24500 | Posted
TX-52-03-3 | 2026-03-27 | 5.2 | SUB | VEN-PMO-003 | Project Assurance Group | PO-52-3 | Project Controls — specialist subcontract | 35000 | Posted
TX-52-04-1 | 2026-04-27 | 5.2 | MAT | VEN-PMO-001 | ControlWorks Consulting | PO-52-1 | Project Controls — primary progress invoice | 45500 | Posted
TX-52-05-2 | 2026-05-27 | 5.2 | LAB | VEN-PMO-002 | Integrated Site Support | PO-52-2 | Project Controls — support services | 52500 | Posted
TX-52-06-3 | 2026-06-26 | 5.2 | SUB | VEN-PMO-003 | Project Assurance Group | PO-52-3 | Project Controls — specialist subcontract | 56000 | Posted
TX-52-07-2 | 2026-07-28 | 5.2 | LAB | VEN-PMO-002 | Integrated Site Support | PO-52-2 | Project Controls — support services | 56000 | Posted
TX-52-08-1 | 2026-08-27 | 5.2 | MAT | VEN-PMO-001 | ControlWorks Consulting | PO-52-1 | Project Controls — primary progress invoice | 63000 | Posted
TX-53-01-1 | 2026-01-28 | 5.3 | MAT | VEN-PMO-001 | ControlWorks Consulting | PO-53-1 | HSE, Quality & Site Services — primary progress invoice | 23800 | Posted
TX-53-02-2 | 2026-02-25 | 5.3 | LAB | VEN-PMO-002 | Integrated Site Support | PO-53-2 | HSE, Quality & Site Services — support services | 33320 | Posted
TX-53-03-3 | 2026-03-27 | 5.3 | SUB | VEN-PMO-003 | Project Assurance Group | PO-53-3 | HSE, Quality & Site Services — specialist subcontract | 47600 | Posted
TX-53-04-1 | 2026-04-27 | 5.3 | MAT | VEN-PMO-001 | ControlWorks Consulting | PO-53-1 | HSE, Quality & Site Services — primary progress invoice | 61880 | Posted
TX-53-05-2 | 2026-05-27 | 5.3 | LAB | VEN-PMO-002 | Integrated Site Support | PO-53-2 | HSE, Quality & Site Services — support services | 71400 | Posted
TX-53-06-3 | 2026-06-26 | 5.3 | SUB | VEN-PMO-003 | Project Assurance Group | PO-53-3 | HSE, Quality & Site Services — specialist subcontract | 76160 | Posted
TX-53-07-2 | 2026-07-28 | 5.3 | LAB | VEN-PMO-002 | Integrated Site Support | PO-53-2 | HSE, Quality & Site Services — support services | 76160 | Posted
TX-53-08-1 | 2026-08-27 | 5.3 | MAT | VEN-PMO-001 | ControlWorks Consulting | PO-53-1 | HSE, Quality & Site Services — primary progress invoice | 85680 | Posted
TX-31-04-1 | 2026-04-27 | 3.1 | MAT | VEN-CON-001 | Borneo EPC Construction | PO-31-1 | Site Preparation & Civil Works — primary progress invoice | 239200 | Posted
TX-NONWBS-001 | 2026-08-18 |  | IND | VEN-PMO-002 | Integrated Site Support | PO-SITE-99 | Unallocated temporary camp utilities | 86500 | Posted
TX-ORPHAN-001 | 2026-08-20 | 9.9 | MAT | VEN-CON-002 | Nusantara Field Services | PO-LEGACY-01 | Legacy field material pending WBS reassignment | 142000 | Posted
TX-VENDOR-ID-001 | 2026-08-22 | 2.3 | MAT | VEN-PRC-003 | PT Nusantara Piping Solutions | PO-23-2 | Piping fittings expediting invoice | 185000 | Posted

## Commitments
PURCHASE ORDERS & COMMITMENTS — USD
commitment_id | wbs_code | po_number | vendor_id | vendor_name | committed_amount | invoiced_amount | status | commitment_date
COM-21-01 | 2.1 | PO-21-1 | VEN-PRC-001 | Atlas Rotating Equipment | 7600000 | 6100000 | Open | 2026-01-15
COM-21-02 | 2.1 | PO-21-2 | VEN-PRC-002 | Pacific Industrial Supply | 912000 | 610000 | Closed | 2026-04-01
COM-22-01 | 2.2 | PO-22-1 | VEN-PRC-001 | Atlas Rotating Equipment | 2600000 | 2050000 | Open | 2026-01-15
COM-22-02 | 2.2 | PO-22-2 | VEN-PRC-002 | Pacific Industrial Supply | 312000 | 205000 | Open | 2026-04-01
COM-23-01 | 2.3 | PO-23-1 | VEN-PRC-001 | Atlas Rotating Equipment | 3200000 | 2250000 | Open | 2026-01-15
COM-23-02 | 2.3 | PO-23-2 | VEN-PRC-002 | Pacific Industrial Supply | 384000 | 225000 | Open | 2026-04-01
COM-24-01 | 2.4 | PO-24-1 | VEN-PRC-001 | Atlas Rotating Equipment | 2100000 | 1450000 | Open | 2026-01-15
COM-24-02 | 2.4 | PO-24-2 | VEN-PRC-002 | Pacific Industrial Supply | 252000 | 145000 | Open | 2026-04-01
COM-31-01 | 3.1 | PO-31-1 | VEN-CON-001 | Borneo EPC Construction | 1850000 | 1600000 | Open | 2026-03-15
COM-31-02 | 3.1 | PO-31-2 | VEN-CON-002 | Nusantara Field Services | 222000 | 160000 | Closed | 2026-04-01
COM-32-01 | 3.2 | PO-32-1 | VEN-CON-001 | Borneo EPC Construction | 2500000 | 2050000 | Open | 2026-03-15
COM-32-02 | 3.2 | PO-32-2 | VEN-CON-002 | Nusantara Field Services | 300000 | 205000 | Open | 2026-04-01
COM-33-01 | 3.3 | PO-33-1 | VEN-CON-001 | Borneo EPC Construction | 2100000 | 1250000 | Open | 2026-03-15
COM-33-02 | 3.3 | PO-33-2 | VEN-CON-002 | Nusantara Field Services | 252000 | 125000 | Open | 2026-04-01
COM-34-01 | 3.4 | PO-34-1 | VEN-CON-001 | Borneo EPC Construction | 1750000 | 950000 | Open | 2026-03-15
COM-34-02 | 3.4 | PO-34-2 | VEN-CON-002 | Nusantara Field Services | 210000 | 95000 | Open | 2026-04-01
COM-35-01 | 3.5 | PO-35-1 | VEN-CON-001 | Borneo EPC Construction | 1350000 | 650000 | Open | 2026-03-15
COM-35-02 | 3.5 | PO-35-2 | VEN-CON-002 | Nusantara Field Services | 162000 | 65000 | Closed | 2026-04-01
COM-41-01 | 4.1 | PO-41-1 | VEN-COM-001 | Commissioning Dynamics Asia | 680000 | 120000 | Open | 2026-03-15
COM-41-02 | 4.1 | PO-41-2 | VEN-COM-002 | Reliability Test Solutions | 81600 | 12000 | Open | 2026-04-01
COM-42-01 | 4.2 | PO-42-1 | VEN-COM-001 | Commissioning Dynamics Asia | 620000 | 35000 | Open | 2026-03-15
COM-42-02 | 4.2 | PO-42-2 | VEN-COM-002 | Reliability Test Solutions | 74400 | 3500 | Open | 2026-04-01
COM-53-01 | 5.3 | PO-53-1 | VEN-PMO-001 | ControlWorks Consulting | 580000 | 410000 | Open | 2026-03-15
COM-53-02 | 5.3 | PO-53-2 | VEN-PMO-002 | Integrated Site Support | 69600 | 41000 | Open | 2026-04-01

## Schedule
LEVEL 3 CONTROL SCHEDULE — STATUS AT 2026-08-31
activity_id | wbs_code | activity_name | discipline | baseline_start | baseline_finish | actual_start | actual_finish | planned_progress | actual_progress | total_float_days | critical | status
ACT-001 | 1.1 | Process design basis and simulations | Engineering | 2026-01-05 | 2026-03-15 | 2026-01-06 | 2026-01-04 | 100% | 100% | -4 | TRUE | Complete
ACT-002 | 1.2 | Civil and structural IFC package | Engineering | 2026-01-20 | 2026-04-15 | 2026-01-22 | 2026-04-30 | 100% | 100% | -6 | TRUE | Complete
ACT-003 | 1.3 | Electrical and instrument IFC package | Engineering | 2026-02-01 | 2026-05-15 | 2026-02-03 |  | 100% | 92% | -12 | TRUE | In Progress
ACT-004 | 1.4 | Construction workpack release | Engineering | 2026-03-01 | 2026-06-15 | 2026-03-05 |  | 100% | 86% | -8 | TRUE | In Progress
ACT-005 | 2.1 | Compressor package engineering | Procurement | 2026-01-15 | 2026-04-30 | 2026-01-18 | 2026-05-20 | 100% | 100% | -15 | TRUE | Complete
ACT-006 | 2.1 | Compressor fabrication and testing | Procurement | 2026-03-01 | 2026-08-10 | 2026-03-05 |  | 100% | 78% | -28 | TRUE | In Progress
ACT-007 | 2.2 | Pressure vessel fabrication | Procurement | 2026-02-15 | 2026-07-20 | 2026-02-20 |  | 100% | 88% | -10 | TRUE | In Progress
ACT-008 | 2.3 | Piping bulk delivery batch 1 | Procurement | 2026-03-01 | 2026-06-30 | 2026-03-10 | 2026-07-18 | 100% | 100% | -5 | FALSE | Complete
ACT-009 | 2.3 | Piping bulk delivery batch 2 | Procurement | 2026-05-01 | 2026-08-15 | 2026-05-08 |  | 100% | 70% | -18 | TRUE | In Progress
ACT-010 | 2.4 | Switchgear and instrument delivery | Procurement | 2026-04-01 | 2026-09-15 | 2026-04-10 |  | 82% | 60% | 4 | FALSE | In Progress
ACT-011 | 3.1 | Site grading and drainage | Construction | 2026-02-15 | 2026-05-30 | 2026-02-20 | 2026-06-12 | 100% | 100% | -4 | FALSE | Complete
ACT-012 | 3.1 | Control building civil works | Construction | 2026-04-01 | 2026-08-15 | 2026-04-05 |  | 100% | 82% | -12 | TRUE | In Progress
ACT-013 | 3.2 | Compressor foundation construction | Construction | 2026-04-15 | 2026-07-31 | 2026-04-20 |  | 100% | 48% | -32 | TRUE | In Progress
ACT-014 | 3.2 | Pipe rack foundation construction | Construction | 2026-05-01 | 2026-08-10 | 2026-05-06 |  | 100% | 52% | -20 | TRUE | In Progress
ACT-015 | 3.3 | Compressor skid erection | Construction | 2026-07-15 | 2026-09-30 | 2026-07-25 |  | 55% | 22% | -14 | TRUE | In Progress
ACT-016 | 3.3 | Vessel and cooler erection | Construction | 2026-07-01 | 2026-09-10 | 2026-07-08 |  | 72% | 38% | -9 | TRUE | In Progress
ACT-017 | 3.4 | Shop spool fabrication | Construction | 2026-05-15 | 2026-08-20 | 2026-05-20 |  | 100% | 66% | -16 | TRUE | In Progress
ACT-018 | 3.4 | Field piping installation | Construction | 2026-07-01 | 2026-11-15 | 2026-07-10 |  | 42% | 19% | 6 | FALSE | In Progress
ACT-019 | 3.5 | Cable tray installation | Construction | 2026-07-01 | 2026-10-15 | 2026-07-12 |  | 48% | 20% | 3 | FALSE | In Progress
ACT-020 | 3.5 | Instrument installation | Construction | 2026-08-01 | 2026-11-30 | 2026-08-12 |  | 18% | 8% | 8 | FALSE | In Progress
ACT-021 | 4.1 | Systemization and turnover dossiers | Commissioning | 2026-09-01 | 2026-11-30 |  |  | 0% | 0% | 5 | FALSE | Not Started
ACT-022 | 4.2 | Commissioning and performance test | Commissioning | 2026-12-01 | 2027-02-15 |  |  | 0% | 0% | 0 | TRUE | Not Started
ACT-023 | 5.1 | Project management and reporting | Project Management | 2026-01-01 | 2027-02-28 | 2026-01-01 |  | 58% | 58% | 0 | FALSE | In Progress
ACT-024 | 5.2 | Cost and schedule controls | Project Controls | 2026-01-01 | 2027-02-28 | 2026-01-01 |  | 58% | 58% | 0 | FALSE | In Progress
ACT-025 | 5.3 | HSE and quality surveillance | HSE/Quality | 2026-02-01 | 2027-02-15 | 2026-02-01 |  | 55% | 52% | 2 | FALSE | In Progress

## Progress
MONTHLY PHYSICAL PROGRESS — CUMULATIVE
progress_id | period | wbs_code | planned_progress | actual_progress | variance | status
PRG-11-01 | 2026-01-31 | 1.1 | 36.25% | 29.75% | -6.5% | Approved
PRG-11-02 | 2026-02-28 | 1.1 | 47.5% | 41.5% | -6% | Approved
PRG-11-03 | 2026-03-31 | 1.1 | 58.75% | 53.25% | -5.5% | Approved
PRG-11-04 | 2026-04-30 | 1.1 | 70% | 65% | -5% | Approved
PRG-11-05 | 2026-05-31 | 1.1 | 81.25% | 76.75% | -4.5% | Approved
PRG-11-06 | 2026-06-30 | 1.1 | 92.5% | 88.5% | -4% | Approved
PRG-11-07 | 2026-07-31 | 1.1 | 100% | 100% | 0% | Approved
PRG-11-08 | 2026-08-31 | 1.1 | 100% | 100% | 0% | Approved
PRG-12-01 | 2026-01-31 | 1.2 | 36.25% | 29.75% | -6.5% | Approved
PRG-12-02 | 2026-02-28 | 1.2 | 47.5% | 41.5% | -6% | Approved
PRG-12-03 | 2026-03-31 | 1.2 | 58.75% | 53.25% | -5.5% | Approved
PRG-12-04 | 2026-04-30 | 1.2 | 70% | 65% | -5% | Approved
PRG-12-05 | 2026-05-31 | 1.2 | 81.25% | 76.75% | -4.5% | Approved
PRG-12-06 | 2026-06-30 | 1.2 | 92.5% | 88.5% | -4% | Approved
PRG-12-07 | 2026-07-31 | 1.2 | 100% | 100% | 0% | Approved
PRG-12-08 | 2026-08-31 | 1.2 | 100% | 100% | 0% | Approved
PRG-13-01 | 2026-01-31 | 1.3 | 36.25% | 27.37% | -8.88% | Approved
PRG-13-02 | 2026-02-28 | 1.3 | 47.5% | 38.18% | -9.32% | Approved
PRG-13-03 | 2026-03-31 | 1.3 | 58.75% | 48.99% | -9.76% | Approved
PRG-13-04 | 2026-04-30 | 1.3 | 70% | 59.8% | -10.2% | Approved
PRG-13-05 | 2026-05-31 | 1.3 | 81.25% | 70.61% | -10.64% | Approved
PRG-13-06 | 2026-06-30 | 1.3 | 92.5% | 81.42% | -11.08% | Approved
PRG-13-07 | 2026-07-31 | 1.3 | 100% | 92% | -8% | Approved
PRG-13-08 | 2026-08-31 | 1.3 | 100% | 92% | -8% | Approved
PRG-14-01 | 2026-01-31 | 1.4 | 36.25% | 25.58% | -10.67% | Approved
PRG-14-02 | 2026-02-28 | 1.4 | 47.5% | 35.69% | -11.81% | Approved
PRG-14-03 | 2026-03-31 | 1.4 | 58.75% | 45.8% | -12.95% | Approved
PRG-14-04 | 2026-04-30 | 1.4 | 70% | 55.9% | -14.1% | Approved
PRG-14-05 | 2026-05-31 | 1.4 | 81.25% | 66% | -15.25% | Approved
PRG-14-06 | 2026-06-30 | 1.4 | 92.5% | 76.11% | -16.39% | Approved
PRG-14-07 | 2026-07-31 | 1.4 | 100% | 86% | -14% | Approved
PRG-14-08 | 2026-08-31 | 1.4 | 100% | 86% | -14% | Approved
PRG-21-01 | 2026-01-31 | 2.1 | 36.25% | 23.21% | -13.04% | Approved
PRG-21-02 | 2026-02-28 | 2.1 | 47.5% | 32.37% | -15.13% | Approved
PRG-21-03 | 2026-03-31 | 2.1 | 58.75% | 41.54% | -17.21% | Approved
PRG-21-04 | 2026-04-30 | 2.1 | 70% | 50.7% | -19.3% | Approved
PRG-21-05 | 2026-05-31 | 2.1 | 81.25% | 59.86% | -21.39% | Approved
PRG-21-06 | 2026-06-30 | 2.1 | 92.5% | 69.03% | -23.47% | Approved
PRG-21-07 | 2026-07-31 | 2.1 | 100% | 78% | -22% | Approved
PRG-21-08 | 2026-08-31 | 2.1 | 100% | 78% | -22% | Approved
PRG-22-01 | 2026-01-31 | 2.2 | 36.25% | 26.18% | -10.07% | Approved
PRG-22-02 | 2026-02-28 | 2.2 | 47.5% | 36.52% | -10.98% | Approved
PRG-22-03 | 2026-03-31 | 2.2 | 58.75% | 46.86% | -11.89% | Approved
PRG-22-04 | 2026-04-30 | 2.2 | 70% | 57.2% | -12.8% | Approved
PRG-22-05 | 2026-05-31 | 2.2 | 81.25% | 67.54% | -13.71% | Approved
PRG-22-06 | 2026-06-30 | 2.2 | 92.5% | 77.88% | -14.62% | Approved
PRG-22-07 | 2026-07-31 | 2.2 | 100% | 88% | -12% | Approved
PRG-22-08 | 2026-08-31 | 2.2 | 100% | 88% | -12% | Approved
PRG-23-01 | 2026-01-31 | 2.3 | 36.25% | 20.83% | -15.42% | Approved
PRG-23-02 | 2026-02-28 | 2.3 | 47.5% | 29.05% | -18.45% | Approved
PRG-23-03 | 2026-03-31 | 2.3 | 58.75% | 37.27% | -21.48% | Approved
PRG-23-04 | 2026-04-30 | 2.3 | 70% | 45.5% | -24.5% | Approved
PRG-23-05 | 2026-05-31 | 2.3 | 81.25% | 53.72% | -27.53% | Approved
PRG-23-06 | 2026-06-30 | 2.3 | 92.5% | 61.95% | -30.55% | Approved
PRG-23-07 | 2026-07-31 | 2.3 | 100% | 70% | -30% | Approved
PRG-23-08 | 2026-08-31 | 2.3 | 100% | 70% | -30% | Approved
PRG-24-01 | 2026-01-31 | 2.4 | 29.72% | 17.85% | -11.87% | Approved
PRG-24-02 | 2026-02-28 | 2.4 | 38.95% | 24.9% | -14.05% | Approved
PRG-24-03 | 2026-03-31 | 2.4 | 48.18% | 31.95% | -16.23% | Approved
PRG-24-04 | 2026-04-30 | 2.4 | 57.4% | 39% | -18.4% | Approved
PRG-24-05 | 2026-05-31 | 2.4 | 66.63% | 46.05% | -20.58% | Approved
PRG-24-06 | 2026-06-30 | 2.4 | 75.85% | 53.1% | -22.75% | Approved
PRG-24-07 | 2026-07-31 | 2.4 | 82% | 60% | -22% | Approved
PRG-24-08 | 2026-08-31 | 2.4 | 82% | 60% | -22% | Approved
PRG-31-01 | 2026-01-31 | 3.1 | 36.25% | 24.39% | -11.86% | Approved
PRG-31-02 | 2026-02-28 | 3.1 | 47.5% | 34.03% | -13.47% | Approved
PRG-31-03 | 2026-03-31 | 3.1 | 58.75% | 43.66% | -15.09% | Approved
PRG-31-04 | 2026-04-30 | 3.1 | 70% | 53.3% | -16.7% | Approved
PRG-31-05 | 2026-05-31 | 3.1 | 81.25% | 62.93% | -18.32% | Approved
PRG-31-06 | 2026-06-30 | 3.1 | 92.5% | 72.57% | -19.93% | Approved
PRG-31-07 | 2026-07-31 | 3.1 | 100% | 82% | -18% | Approved
PRG-31-08 | 2026-08-31 | 3.1 | 100% | 82% | -18% | Approved
PRG-32-01 | 2026-01-31 | 3.2 | 36.25% | 12.5% | -23.75% | Approved
PRG-32-02 | 2026-02-28 | 3.2 | 47.5% | 17.43% | -30.07% | Approved
PRG-32-03 | 2026-03-31 | 3.2 | 58.75% | 22.37% | -36.38% | Approved
PRG-32-04 | 2026-04-30 | 3.2 | 70% | 27.3% | -42.7% | Approved
PRG-32-05 | 2026-05-31 | 3.2 | 81.25% | 32.23% | -49.02% | Approved
PRG-32-06 | 2026-06-30 | 3.2 | 92.5% | 37.17% | -55.33% | Approved
PRG-32-07 | 2026-07-31 | 3.2 | 100% | 42% | -58% | Approved
PRG-32-08 | 2026-08-31 | 3.2 | 100% | 42% | -58% | Approved
PRG-33-01 | 2026-01-31 | 3.3 | 26.1% | 9.52% | -16.58% | Approved
PRG-33-02 | 2026-02-28 | 3.3 | 34.2% | 13.28% | -20.92% | Approved
PRG-33-03 | 2026-03-31 | 3.3 | 42.3% | 17.04% | -25.26% | Approved
PRG-33-04 | 2026-04-30 | 3.3 | 50.4% | 20.8% | -29.6% | Approved
PRG-33-05 | 2026-05-31 | 3.3 | 58.5% | 24.56% | -33.94% | Approved
PRG-33-06 | 2026-06-30 | 3.3 | 66.6% | 28.32% | -38.28% | Approved
PRG-33-07 | 2026-07-31 | 3.3 | 72% | 32% | -40% | Approved
PRG-33-08 | 2026-08-31 | 3.3 | 72% | 32% | -40% | Approved
PRG-34-01 | 2026-01-31 | 3.4 | 15.23% | 5.65% | -9.58% | Approved
PRG-34-02 | 2026-02-28 | 3.4 | 19.95% | 7.89% | -12.06% | Approved
PRG-34-03 | 2026-03-31 | 3.4 | 24.68% | 10.12% | -14.56% | Approved
PRG-34-04 | 2026-04-30 | 3.4 | 29.4% | 12.35% | -17.05% | Approved
PRG-34-05 | 2026-05-31 | 3.4 | 34.13% | 14.58% | -19.55% | Approved
PRG-34-06 | 2026-06-30 | 3.4 | 38.85% | 16.82% | -22.03% | Approved
PRG-34-07 | 2026-07-31 | 3.4 | 42% | 19% | -23% | Approved
PRG-34-08 | 2026-08-31 | 3.4 | 42% | 19% | -23% | Approved
PRG-35-01 | 2026-01-31 | 3.5 | 12.69% | 4.76% | -7.93% | Approved
PRG-35-02 | 2026-02-28 | 3.5 | 16.62% | 6.64% | -9.98% | Approved
PRG-35-03 | 2026-03-31 | 3.5 | 20.56% | 8.52% | -12.04% | Approved
PRG-35-04 | 2026-04-30 | 3.5 | 24.5% | 10.4% | -14.1% | Approved
PRG-35-05 | 2026-05-31 | 3.5 | 28.44% | 12.28% | -16.16% | Approved
PRG-35-06 | 2026-06-30 | 3.5 | 32.38% | 14.16% | -18.22% | Approved
PRG-35-07 | 2026-07-31 | 3.5 | 35% | 16% | -19% | Approved
PRG-35-08 | 2026-08-31 | 3.5 | 35% | 16% | -19% | Approved
PRG-41-01 | 2026-01-31 | 4.1 | 0% | 0% | 0% | Approved
PRG-41-02 | 2026-02-28 | 4.1 | 0% | 0% | 0% | Approved
PRG-41-03 | 2026-03-31 | 4.1 | 0% | 0% | 0% | Approved
PRG-41-04 | 2026-04-30 | 4.1 | 0% | 0% | 0% | Approved
PRG-41-05 | 2026-05-31 | 4.1 | 0% | 0% | 0% | Approved
PRG-41-06 | 2026-06-30 | 4.1 | 0% | 0% | 0% | Approved
PRG-41-07 | 2026-07-31 | 4.1 | 0% | 0% | 0% | Approved
PRG-41-08 | 2026-08-31 | 4.1 | 0% | 0% | 0% | Approved
PRG-42-01 | 2026-01-31 | 4.2 | 0% | 0% | 0% | Approved
PRG-42-02 | 2026-02-28 | 4.2 | 0% | 0% | 0% | Approved
PRG-42-03 | 2026-03-31 | 4.2 | 0% | 0% | 0% | Approved
PRG-42-04 | 2026-04-30 | 4.2 | 0% | 0% | 0% | Approved
PRG-42-05 | 2026-05-31 | 4.2 | 0% | 0% | 0% | Approved
PRG-42-06 | 2026-06-30 | 4.2 | 0% | 0% | 0% | Approved
PRG-42-07 | 2026-07-31 | 4.2 | 0% | 0% | 0% | Approved
PRG-42-08 | 2026-08-31 | 4.2 | 0% | 0% | 0% | Approved
PRG-51-01 | 2026-01-31 | 5.1 | 21.03% | 17.25% | -3.78% | Approved
PRG-51-02 | 2026-02-28 | 5.1 | 27.55% | 24.07% | -3.48% | Approved
PRG-51-03 | 2026-03-31 | 5.1 | 34.08% | 30.88% | -3.2% | Approved
PRG-51-04 | 2026-04-30 | 5.1 | 40.6% | 37.7% | -2.9% | Approved
PRG-51-05 | 2026-05-31 | 5.1 | 47.12% | 44.51% | -2.61% | Approved
PRG-51-06 | 2026-06-30 | 5.1 | 53.65% | 51.33% | -2.32% | Approved
PRG-51-07 | 2026-07-31 | 5.1 | 58% | 58% | 0% | Approved
PRG-51-08 | 2026-08-31 | 5.1 | 58% | 58% | 0% | Approved
PRG-52-01 | 2026-01-31 | 5.2 | 21.03% | 17.25% | -3.78% | Approved
PRG-52-02 | 2026-02-28 | 5.2 | 27.55% | 24.07% | -3.48% | Approved
PRG-52-03 | 2026-03-31 | 5.2 | 34.08% | 30.88% | -3.2% | Approved
PRG-52-04 | 2026-04-30 | 5.2 | 40.6% | 37.7% | -2.9% | Approved
PRG-52-05 | 2026-05-31 | 5.2 | 47.12% | 44.51% | -2.61% | Approved
PRG-52-06 | 2026-06-30 | 5.2 | 53.65% | 51.33% | -2.32% | Approved
PRG-52-07 | 2026-07-31 | 5.2 | 58% | 58% | 0% | Approved
PRG-52-08 | 2026-08-31 | 5.2 | 58% | 58% | 0% | Approved
PRG-53-01 | 2026-01-31 | 5.3 | 19.94% | 15.47% | -4.47% | Approved
PRG-53-02 | 2026-02-28 | 5.3 | 26.13% | 21.58% | -4.55% | Approved
PRG-53-03 | 2026-03-31 | 5.3 | 32.31% | 27.69% | -4.62% | Approved
PRG-53-04 | 2026-04-30 | 5.3 | 38.5% | 33.8% | -4.7% | Approved
PRG-53-05 | 2026-05-31 | 5.3 | 44.69% | 39.91% | -4.78% | Approved
PRG-53-06 | 2026-06-30 | 5.3 | 50.88% | 46.02% | -4.86% | Approved
PRG-53-07 | 2026-07-31 | 5.3 | 55% | 52% | -3% | Approved
PRG-53-08 | 2026-08-31 | 5.3 | 55% | 108% | 53% | Approved

## Scenario_Notes
Scenario Control Totals & Seeded Risk Register
Control total | Calculated value
Approved budget
Posted actual cost
Gross commitments
Activities with negative float
Progress records above 100%
Model status | PASS — workbook deliberately contains analyzable project risks
Risk theme | Affected area | Business rationale | Intentional? | Expected engine behavior | User action
Actual cost overrun | WBS 3.2 | Foundation rework and acceleration increase cost above budget | Yes | CST-001 | Review change control and forecast
Commitment exposure | WBS 2.1 / 3.2 | Open PO exposure pushes forecast above approved budget | Yes | CST-002 | Reconcile PO and estimate-to-complete
Cost spike | WBS 3.3 | Heavy August mobilization and erection billing | Yes | CST-003 | Validate earned progress and accrual timing
Vendor concentration | WBS 2.1 | OEM dominates compressor-package spend | Yes | CST-004 | Monitor OEM performance and contingency
High-value transaction | WBS 2.2 | Fabrication milestone is material to package budget | Yes | CST-005 | Verify milestone evidence
Schedule delay | Critical construction | Foundations and compressor package are behind baseline | Yes | SCH-001—SCH-005 | Run recovery planning
Progress lag | WBS 3.2 / 3.3 | Physical progress trails plan and is flat in latest period | Yes | PRG-001 / PRG-003 | Validate quantities and productivity
Data quality | Actual cost / vendor | One duplicate, one missing WBS, one orphan, one identity inconsistency | Yes | DQ-001—DQ-005 | Correct source-system master data